## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_138 | Construction of a concrete deck foot bridge at Mbabvi foot bridge | construction of a concrete deck foot bridge at Mbabvi river in T/A njewa | to improve quality of mobility of people during rainy season | construction | completion | 2022-08-25T11:38:11Z | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-31T00:00:00Z | 137 | transport | 2022-03-31T00:00:00Z | 2072-03-31T00:00:00Z | 18263 | 0.00 | 2022-03-31T00:00:00Z | the contract period was extended | the value was over budget due to the additional budget | construction of a concrete deck footbridge at Mbabvi river | there were a bit of additional works after another appraisal was conducted during the construction | 33759097.73 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_138 | 43 | LDC/GESD/2021-22/CDB/03G/4 | Construction of 30 Ton Concrete Deck Bridges-Mbavi river concrete deck Foot bridge - T/A Njewa | the contract is not closed so as to allow change of scope if need be | active | construction | 24999354.12 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 24999354.12 | MWK | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-31T00:00:00Z | 137

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_138 | 36 | contractSigned | Construction of 30 Ton Concrete Deck Bridges-Mbavi river concrete deck Foot bridge - T/A Njewa | signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_138 | 123 | T/A Njewa | Polygon | [[[33.630427,-13.963981],[33.630009,-13.964538],[33.630459,-13.965006],[33.630947,-13.96472],[33.630888,-13.964132],[33.630427,-13.963981]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_138 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | administrativeEntity;procuringEntity
oc4ids-iuq5r5_138 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org