## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_144 | Construction of A vendor's Market shed at Namitete Market | Construction of a vendor's market shed | to provide a suitable trading place for local suppliers and consumers | construction | completion | 2022-08-25T11:39:01Z | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-31T00:00:00Z | 137 | economy | 2022-03-31T00:00:00Z | 2062-03-31T00:00:00Z | 14610 | 0.00 | 2022-03-31T00:00:00Z | the project took more than 90 days to be completed due to a number of delays | the project was a little bit over budget due to the change in prices of materials | Construction of a vendor's market shed | the scope of the project did not change | 34840724.99 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_144 | 46 | LDC/GESD/2021-22/VMS/06G/2 | Construction of a vendor's marked shed at Namitete Market | the contract is not closed so as to allow change of scope if need be | active | construction | 33813757.34 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 33813757.34 | MWK | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-31T00:00:00Z | 137

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_144 | 42 | contractSigned | Construction of a vendor's Market shed at T/A Kalolo | the signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_144 | 134 | T/A Kalolo | Polygon | [[[33.169549,-13.922589],[33.169591,-13.923141],[33.170418,-13.923109],[33.170342,-13.922568],[33.169549,-13.922589]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_144 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_144 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org