## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_146 | Construction of an OPD block at Chitsime Health Centre | construction of an Outpatient department office block | to improve health care provision services | construction | completion | 2022-08-25T04:27:28Z | 2022-02-16T00:00:00Z | 2022-05-17T00:00:00Z | 2022-05-17T00:00:00Z | 90 | health | 2022-03-14T00:00:00Z | 2062-03-14T00:00:00Z | 14610 | 0.00 | 2022-03-14T00:00:00Z | the project was completed before the contract duration elapsed | the project was completed over the budget because of the rise in cost of construction materials | construction of an Out Patient Department Block | the scope did not change over the course of the project | 48772862.78 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_146 | 47 | LDC/GESD/2021-22/HF/04G/2 | Construction of an OPD Block at Chitsime Health centre | the contract is not closed so as to allow change of scope if need be | active | construction | 45000000 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 45000000 | MWK | 2022-02-16T00:00:00Z | 2022-05-17T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_146 | 43 | contractSigned | Construction of an OPD Block at Chitsime Health centre | the signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_146 | 136 | T/A Kalumba | Polygon | [[[33.792175,-14.094544],[33.791869,-14.094419],[33.792046,-14.094101],[33.792341,-14.094205],[33.792175,-14.094544]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_146 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_146 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org