## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_147 | Construction of a box culvert at Kasanda River | Construction of a box culvert at Kasanda river and other associated works | to improve mobility of people and vehicles during wet season | construction | completion | 2022-08-25T11:40:34Z | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-08T00:00:00Z | 114 | transport | 2022-03-08T00:00:00Z | 2072-03-08T00:00:00Z | 18263 | 0.00 | 2022-03-08T00:00:00Z | the project was completed after the contract period | the project was completed within budget | Construction of a box culvert and other associated works | the scope did not change | 23674208.48 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_147 | 48 | LDC/GESD/2021-22/CDB/03G/2 | Construction of a Box Culvert at Kasanda river | the contract is not closed so as to enable change of scope if need be | active | construction | 22494765.48 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 22494765.48 | MWK | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 2022-03-08T00:00:00Z | 114

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_147 | 44 | contractSigned | Construction of a Box Culvert at Kasanda river | the signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_147 | 137 | T/A Khongoni | Polygon | [[[33.370414,-13.759079],[33.370768,-13.75912],[33.370693,-13.75836],[33.370392,-13.758401],[33.370414,-13.759079]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_147 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_147 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org