## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_154 | Construction of a staff house at Mngoni health centre | Construction of a staff house | to help with the accommodation of heath care personnel so as to reduce time taken to reach duty station | construction | completion | 2022-08-26T05:26:17Z | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 90 | health | 2022-01-31T00:00:00Z | 2062-01-31T00:00:00Z | 14610 | 2021-05-13T00:00:00Z | 2021-05-13T00:00:00Z | 26500000 | MWK | 2022-03-31T00:00:00Z | the project was completed within the stipulated period | the project was completed a bit over budget due to the rising cost in construction materials | construction of a staff house | the scope was not changed | 26987499.29 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_154 | 1 | 94 | Construction of a staff house | 26500000 | MWK | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 22 | Lilongwe District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_154 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_154 | 52 | LDC/GESD/2021-22/SH/02G/1 | Construction of a staff house at Mngoni health centre | the contract is not closed so as to enable change of scope if need be. | active | construction | 26500000 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 26500000 | MWK | 2021-11-14T00:00:00Z | 2022-02-12T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_154 | 49 | contractSigned | Construction of a staff house at Mngoni health centre | the signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_154 | 142 | T/A Mtema | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_154 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_154 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org