## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_156 | Construction of a traditional court at Mpenu Headquarters T/A Mazengera | Construction of a traditional court and two VIP Toilets | to provide a proper place for traditional court cases to be heard and judged | construction | completion | 2022-08-26T06:37:16Z | 2021-11-15T00:00:00Z | 2022-02-13T00:00:00Z | 2022-04-29T00:00:00Z | 165 | governance | 2022-04-29T00:00:00Z | 2062-04-29T00:00:00Z | 14610 | 0.00 | 2022-04-29T00:00:00Z | the project was completed beyond the original completion date | the value was a bit over budget due to the rising cost of construction materials | Construction of a traditional court and two VIP Toilets | the scope of the project did not change till the end | 28558541.09 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_156 | 54 | LDC/DDF/2021-22/OB/03D/4 | Construction of a traditional court at Mpenu headquarters | the contract was not closed to allow change of scope if need be | active | construction | 25000000 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 25000000 | MWK | 2021-11-15T00:00:00Z | 2022-02-13T00:00:00Z | 2022-04-29T00:00:00Z | 165

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_156 | 58 | contractSigned | Construction of a traditional court at Mpenu headquarters in T/A Mazengera | the signed contract agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_156 | 143 | T/A Mazengera | Polygon | [[[33.9739,-14.085922],[33.97442,-14.085907],[33.974259,-14.085548],[33.973777,-14.085568],[33.9739,-14.085922]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url
oc4ids-iuq5r5_156 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_156 | 51 | Malawi Government | Capital Hill | Lilongwe | Central Region | 0000 | Malawi | Malawi Government | info@malawi.gov.mw | 0000 | funder | 0000 | https://www.malawi.gov.mw