## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/finalValue/currency
oc4ids-iuq5r5_206 | Construction of market shed at Mulipa market shed in Machinga Central East | Construction of market shed with concrete benches | To ease space for vendors to display their merchandise | construction | implementation | 2022-09-13T08:16:16Z | 2022-07-28T00:00:00Z | 2022-08-30T00:00:00Z | 2022-10-05T00:00:00Z | 69 | economy.agriculture | 2022-08-19T00:00:00Z | 2025-01-23T00:00:00Z | 888 | 0.00 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/externalReference | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_206 | 69 | 091/MHGDC/W/DDF/PUBLIC WORKS/MULIPA MARKET SHED/09/06/2022 | 002 | Construction of market shed at Mulipa market shed in Machinga Central East | Construction of market shed with concrete benches | active | construction | 36852450 | MWK | 125 | Phalombe District Council | 125 | Phalombe District Council | 36852450 | MWK | 2022-07-28T00:00:00Z | 2022-08-24T00:00:00Z | 27

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_206 | 183 | Mulipa Trading Centre | MH | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_206 | 125 | Phalombe District Council | 0000 | Phalombe | Southern Region | 0000 | Malawi | Phalombe District Council | 0000 | 0000 | https://0000 | procuringEntity;administrativeEntity