## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_213 | Chaweta primary school electrical installation | installation of electricity in classrooms and staff houses | improve service delivery | construction | completion | 2023-09-18T10:10:04Z | 2022-07-22T00:00:00Z | 2022-09-22T00:00:00Z | 2022-09-30T00:00:00Z | 70 | education | 2022-07-30T00:00:00Z | 2062-09-30T00:00:00Z | 2062-09-30T00:00:00Z | 14672 | 2022-01-03T00:00:00Z | 2022-04-01T00:00:00Z | 18000000 | MWK | 2022-09-22T00:00:00Z | COMPLETED | THERE WAS NO VARRIATION OF COST | ELECTRIFICATION OF CHAWETA PRIMARY SCHOOL | THE PROJECT WAS COMPLETED IN TIME | 17150000 | MWK