## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_23 | MALAWI SECOND AGRICULTURESECTOR WIDW APPROACH | Upgrading of Junction M001(Chinyamula to Mphepozinai (10km) to Low Volume Seal Roads (LVR) Standards in Ntcheu District | To help improve transportation of Farm Inputs and Farm Products | construction | completion | 2021-11-15T11:03:16Z | 2019-08-05T00:00:00Z | 2020-11-30T00:00:00Z | 2021-03-26T00:00:00Z | 599 | transport;transport.road | 2020-04-01T00:00:00Z | 2025-04-01T00:00:00Z | 2026-04-01T00:00:00Z | 2191 | 0.00 | 2020-11-30T00:00:00Z | Successfully completed with addenda | 1,150,000,000.00 | Only 7kms done | Upgraded road (7kms) and construction of 9m Concrete Deck Bridge | 1150000000 | MWK