## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_240 | Construction of a 30 tonne concrete deck bridge at Kanjamwana | construction of a 30 tonne concrete deck bridge | to improve the quality of transportation during rainy season | construction | implementation | 2025-03-12T10:52:05Z | 2023-01-13T00:00:00Z | 2023-04-13T00:00:00Z | 2023-05-13T00:00:00Z | 120 | transport.road | 2023-04-13T00:00:00Z | 2073-04-13T00:00:00Z | 2093-04-13T00:00:00Z | 25568 | 2022-03-23T00:00:00Z | 2022-03-23T00:00:00Z | 59250000 | MWK | 2023-10-03T00:00:00Z | the project has been completed | the revision in scope lowered the cost | construction of 6 cell box culvert with retaining walls with associated works | the scope was modified due to the prevailing site conditions | 58094784.98 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/uri | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_240 | 1 | 240 | CONSTRUCTION OF KANJAMWANA BRIDGE | https://NA | 58999475.6 | MWK | 2023-01-13T00:00:00Z | 2023-04-13T00:00:00Z | 2023-06-30T00:00:00Z | 273 | Samwamwa civil engineering

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_240 | 1

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_240 | 77 | contractSigned | Construction of a 30 tonne concrete deck bridge at Mwanang'ombe River on Mkomba to Chikanda road | the signed contract document | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_240 | 204 | T/A Kalumbu | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_240 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity
oc4ids-iuq5r5_240 | 273 | Samwamwa civil engineering | Lilongwe | Lilongwe |  |  | Malawi | Samwamwa civil engineering | hsshsj@yahoo | 00000 | contractor