## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_328 | Construction of Market Shed at Chitipa Boma | The project will construct a market shed at Chitipa Boma | The project will provide conducive trading place for vendors to ply their trade and reduce roadside accidents due to trading along the streets | construction | completion | 2023-05-30T13:48:30Z | 2022-11-29T00:00:00Z | 2023-03-29T00:00:00Z | 2023-04-30T00:00:00Z | 152 | economy | 2023-04-30T00:00:00Z | 2063-04-15T00:00:00Z | 2065-04-15T00:00:00Z | 15326 | 2022-11-01T00:00:00Z | 2022-11-29T00:00:00Z | 26931265 | MWK | 2023-04-30T00:00:00Z | Finishing works in progress i.e painting and decoration | 26931265 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_328 | 1 | 141 | The Funding is from GESD and it comprises of Substructure 30%, Superstructure and roof 38%, finishing and retention 32% | 26931265 | MWK | 2022-11-29T00:00:00Z | 2023-03-29T00:00:00Z | 62 | Chitipa District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_328 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_328 | 379 | Contract/29/11/22 | Contract | The project contract document between Chitipa District Council and Lingstone Construction | closed | construction | 62 | Chitipa District Council | 62 | Chitipa District Council | 26931265 | MWK | 2022-12-06T00:00:00Z | 2023-03-06T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_328 | 271 | contractSigned | Contract | Project contract document | https:// | application/pdf
oc4ids-iuq5r5_328 | 272 | defaultEvents | Picture | The completed Boma Market Shed | https:// | image/jpeg

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_328 | 385 | Construction of Chitipa Boma market shade | CT | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_328 | 62 | Chitipa District Council | P.O. Box 1, Chitipa | Chitipa | Northern Region | 0000 | Malawi | Chitipa District Council | Email@email.com | 00000000 | procuringEntity;administrativeEntity