## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScope | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_386 | Rehabilitation of Maternity wing at Sambakusi Health Center. | To rehabilitate the maternity wing at Sambakusi Health post. | To reduce Mother and Infant mortality rate, through provision of conducive environment for child delivery | construction | completion | 2023-05-17T16:21:11Z | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92 | health | 2021-04-01T00:00:00Z | 2021-12-01T00:00:00Z | 17000000 | MWK | 2022-03-31T00:00:00Z | 100 Ceiling Works, Plumbing Works, Wards Demarcation, Rest and Bath Rooms Construction, Drainage Works, Delivery Room Partitioning, and Finishing Works done | Health | 14140537 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_386 | 1 | 218 | Approved Budget | 17000000 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_386 | 1 | 219 | Total Project Cost | 14140537 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_386 | 1 | 220 | Expenditure | 14140537 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_386 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_386 | 146 | NS/IPDAC/GESD/WKS/2021-22/01-LOT 6 | Contract Agreement between Ntchisi District Council and LROBERTS Construction | The contract states that the Contractor was paid to execute the rehabilitate Sambakusi Health post | active | construction | 14140537.59 | MWK | 20 | Ntchisi District Council | 20 | Ntchisi District Council | 14140537.59 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_386 | 151 | environmentalImpact | ESMP for rehabilitation of Sambakusi Health Post | The document describes in detail the potential environmental and social impacts associated with the proposed sub project under rehabilitation of Sambakunsi Health Post and outline mitigation measures required to address the identified impacts | https:// | application/pdf
oc4ids-iuq5r5_386 | 175 | contractSigned | Contract Agreement- NS & L.ROBERTS Construction- Rehabilitation of Maternity wing at Sambakusi Health Center. | This is the sgned contract Contract Agreement between Ntchisi District Council and L.ROBERTS Construction- Rehabilitation of Maternity wing at Sambakusi Health Center. | https:// | application/msword

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_386 | 300 | T/A Nthondo | NI | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_386 | 20 | Ntchisi District Council | Box 1 | Ntchisi | Central | Malawi | Ntchisi District Council | email@email.com | 000000000 | procuringEntity;administrativeEntity