## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_398 | Solar water System at Kandodo Village | Drilling & Installation of Mechanized Solar Water System | To improve access to water which is essential for hygiene and sanitation. | construction | completion | 2023-05-17T16:24:31Z | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92 | waterAndWaste | 2021-04-01T00:00:00Z | 2021-12-01T00:00:00Z | 18000000 | MWK | 2022-03-31T00:00:00Z | No boreholes drilled Due to water low yield within the proposed site/area, water supply through mechanization was not ideal and borehole drilling was opted with a hand pumps | 18286065 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_398 | 1 | 207 | Approved Budget | 29000000 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_398 | 1 | 212 | Total Project Cost | 18286065 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_398 | 1 | 213 | Expenditure | 9202737.1 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_398 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_398 | 128 | NS/IPDAC/GESD/WKS/2021-22/01 | Contract Agreement between Ntchisi District Council and Bwalo Civil | The Contractor was paid to execute Drilling of construction of Solar Water system | closed | construction | 18286065 | MWK | 20 | Ntchisi District Council | 20 | Ntchisi District Council | 18286065 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_398 | 145 | environmentalImpact | ESMP for Kandondo Solar Powered water system at T/A Kasakul | The document describes in detail the potential environmental and social impacts associated with the Drilling of a Mechanized Solar Powered water system in Chikho Village in TA Kasakula and outline mitigation measures required to address the identified impacts. | https:// | application/pdf
oc4ids-iuq5r5_398 | 173 | contractSigned | Contract Agreement -NS & Bwalo Civils- construction of a Solar water system | Signed Contract Agreement between Ntchisi District Council and Bwalo Civils for the construction of a Solar water system | https:// | application/msword

## locations
id | locations/0/id | locations/0/description | locations/0/address/countryName | locations/0/address/locality | locations/0/address/region
oc4ids-iuq5r5_398 | 289 | T/a | Malawi
oc4ids-iuq5r5_398 | 290 | T/A Kasakula | Malawi | NI | Central

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_398 | 20 | Ntchisi District Council | Box 1 | Ntchisi | Central | Malawi | Ntchisi District Council | email@email.com | 000000000 | procuringEntity;administrativeEntity