## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_40 | CONTRUCTION OF NDAKWERA CDSS CLASSROOM BLOCK | CONSTRUCTION OF NDAKWERA CDSS CLASSROOM BLOCK | IMPROVE QUALITY EDUCATION SERVICE DELIVERY | construction | completion | 2023-09-06T12:02:22Z | 2022-03-03T00:00:00Z | 2022-06-01T00:00:00Z | 90 | education | 2023-01-04T00:00:00Z | 2074-01-04T00:00:00Z | 18628 | 2021-01-06T00:00:00Z | 2021-04-12T00:00:00Z | 32011425 | MWK | 2021-11-02T00:00:00Z | Classroom block constructed | No addendum was issued | Classroom block constructed with good workmanship | Classroom block constructed completed | 32011425 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_40 | 1 | 27 | CHIKWAWA CENTRAL, NDAKWERA TEACHERS HOUSE, TA | 9979580 | MWK | 2021-06-01T00:00:00Z | 2021-08-30T00:00:00Z | 74 | Noza Building Contractors

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_40 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_40 | 28 | 74 | Noza Building Contractors

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_40 | 28 | 74 | Noza Building Contractors

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_40 | 28 | CKDC/DDF/CENTRAL/WORKS/04 | Construction of Ndakwera teachers house | Construction of Ndakwera teachers house under DDF fund | closed | construction | open | bestValueToGovernment | 1 | 9979580 | MWK | 67 | Chikwawa District Council | 67 | Chikwawa District Council | 9979580 | MWK | 2021-06-01T00:00:00Z | 2021-08-30T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_40 | 25 | evaluationReports | Connstruction of ndakwera teachers house | Evalution report for ndakwera school block | https:// | application/vnd.openxmlformats-officedocument.spreadsheetml.sheet

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_40 | 34 | CHIKWAWA CENTRAL, NDAKWERA TEACHERS HOUSE, TA | Point | 34.822597;-16.167444 | CK | Southern | 265 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_40 | 67 | Chikwawa District Council | Box 000 | Chikwawa | South | 265 | Malawi | Chikwawa District Council | Mail@mail.con | 0000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_40 | 74 | Noza Building Contractors | P.O. Box 117, Nchalo | Blantyre | South |  | Malawi | Noza Building Contractors | mail@mail.com | 0999 408 841 | supplier;tenderer