## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_483 | Construction of Mpamadzi Bridge | Project involved construction of a 10 metre single span concrete deck bridge | The project aimed at improving accessibility between two areas in order to provide economic benefit to the people. | construction | completion | 2023-05-28T06:24:01Z | 2021-08-02T00:00:00Z | 2021-11-01T00:00:00Z | 2021-12-31T00:00:00Z | 151 | economy.agriculture;communications;economy;health | 2021-11-01T00:00:00Z | 2026-11-11T00:00:00Z | 2026-11-11T00:00:00Z | 1836 | 2021-07-01T00:00:00Z | 2021-08-02T00:00:00Z | 30000000 | MWK | 2021-11-11T00:00:00Z | The completed project included a 10 metre single span concrete deck bridge | N/A | COnstruction of abhartment construction, wing walls | The completed project included a 10 metre single span deck bridge | 30000000 | MWK

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_483 | 26 | Ntcheu District Council | Ntcheu | Ntcheu Boma | Central | 0000 | Malawi | Ntcheu District Council | ntcheuDistrict@gov.mw | 09000000000 | administrativeEntity