## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_498 | Construction of Teacher's House at Namutegha Primary School | Construction of the modern teacher's house at Namutegha Primary School | To provide a conducive habitable dwelling residence for teachers hence reducing the pupil-teacher ratio and consequently improving the educational attainment of learners | construction | completion | 2023-06-02T08:42:24Z | 2022-12-22T00:00:00Z | 2023-03-22T00:00:00Z | 2023-06-30T00:00:00Z | 190 | education | 2023-07-14T00:00:00Z | 2123-07-14T00:00:00Z | 36524 | 0.00 | 2023-05-18T00:00:00Z | The structure is finally built with minor completion works remaining | MK30,422,645.36 | The completion certificate not issued | Painting, glazing, drainage works, doors and locks fixing | 30422645.36 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_498 | 377 | Contract/15/12/22 | Contract | Project contract document | active | construction | 30422645.36 | MWK | 62 | Chitipa District Council | 62 | Chitipa District Council | 30422645.36 | MWK | 2022-12-22T00:00:00Z | 2023-03-22T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_498 | 269 | defaultEvents | Picture | The project at the finishing level | https:// | image/jpeg
oc4ids-iuq5r5_498 | 270 | contractSigned | Contract | The Project contract document between Chitipa District Council and Bufama Building Contractors | https:// | application/pdf

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_498 | 62 | Chitipa District Council | P.O. Box 1, Chitipa | Chitipa | Northern Region | 0000 | Malawi | Chitipa District Council | Email@email.com | 00000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_498 | 358 | Bufuma Building Contractors | Chitipa street | Chitipa | North |  | Malawi | Bufuma Building Contractors | Bufuma@gmail.com | 0000 | contractor | 0000