## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_500 | Construction of Vibangalala Maternity Wing | Construction of a maternity wing at Vibangalala in TA Vibangalala. | The project focusses on reducing the distance thereby improving the accessibility of maternal health services. | construction | completion | 2023-06-03T08:03:51Z | 2021-12-21T00:00:00Z | 2022-03-21T00:00:00Z | 90 | health | 0.00 | 2022-05-30T00:00:00Z | All construction works were completed. | None. | none. | All construction works were completed. | 49188877.22 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_500 | 368 | MDC/NCB/GESD/2021/22/07 | Contract details | Contract details of the project. | closed | 49188877.22 | MWK | 54 | M'mbelwa District Council | 54 | M'mbelwa District Council | 49188877.22 | MWK | 2021-12-19T00:00:00Z | 2022-02-17T00:00:00Z | 60

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_500 | 243 | contractSigned | Contract Agreement | Contract Agreement . | https:// | application/pdf
oc4ids-iuq5r5_500 | 244 | minutes | Site visit minutes | Site visit minutes | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document
oc4ids-iuq5r5_500 | 245 | completionCertificate | Completion certificate | Completion certificate. | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_500 | 414 | Vibangalala, TA Mzukuzuku | MZ | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_500 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | https://www.worldbank.org | funder
oc4ids-iuq5r5_500 | 54 | M'mbelwa District Council | P.O. Box 132, Mzimba | Mzimba | Northern Region | 0000 | Malawi | M'mbelwa District Council | Email@email.com | 00000000 |  | administrativeEntity;procuringEntity
oc4ids-iuq5r5_500 | 265 | National Local Goverment | Lilongwe | Lilongwe |  |  | Malawi | National Local Goverment | gsgsf@mnd.com | 000 |  | reviewBody
oc4ids-iuq5r5_500 | 353 | Kathabwa Building Contractor | Mzimba | Mzimba |  |  | Malawi | Kathabwa Building Contractor | @gmail.com | 0000 |  | contractor