## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_502 | CONSTRUCTION OF JUNJU GIRLS HOSTEL | The project involves construction of hostel to accommodate girls at Junju CDSS. The hostel will accomadate80 female learners. It will also carter for beds and mattresses. | difficulty to access secondary education after completion of primary education, leads more teanergers in hard to reach areas drop out of school. as a result there are a lot of teenage pregnancies and early marriages. the hostel will provide accommodation for girls thereby, eliminating walking distances from home to school. girls will have enough time to study, discuss school work and rest after studies. this will in-turn improve pass rate and reduce drop out rate among girl child learners. | construction | implementation | 2023-10-05T08:23:01Z | 2023-02-09T00:00:00Z | 2023-06-18T00:00:00Z | 2023-06-30T00:00:00Z | 150 | education | 2022-10-20T00:00:00Z | 2022-11-20T00:00:00Z | 90423987.56 | MWK | 2023-08-01T00:00:00Z | 100% completed physical progress with remaining little amount in terms of financial progress | 31264432.05 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate
oc4ids-iuq5r5_502 | 354 | MW-RDA-320757-CW-RFB | construction of Junju girls hostel | FIDELIS BUILDING CONTRACTORS, BOX 330, ZOMBA | active | construction | 90423987.56 | MWK | 146 | Rumphi District Council | 146 | Rumphi District Council | 90423987.56 | MWK | 2022-02-06T00:00:00Z | 2022-05-06T00:00:00Z | 2022-05-06T00:00:00Z

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_502 | 202 | contractSigned | CONSTRUCTION OF JUNJU GIRLS HOSTEL | PROJECT INVOLVES CONSTRUCTION OF A GIRLS HOSTEL TO ACCOMADATE 80 STUDENTS. PLUS BEDS ANATRESSES | https:// | application/pdf
oc4ids-iuq5r5_502 | 203 | environmentalImpact | CONSTRUCTION OF JUNJU GIRLS HOSTEL | PROJECT INVLOVES CONSTRUCTION OF A GIRLS HOSTEL WHICH WILL ACCOMODATE 80 STUDENTS; PLUS BEDS AND MATRESSES | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document
oc4ids-iuq5r5_502 | 206 | physicalProgressReport | CONSTRUCTION OF JUNJU GIRLS HOSTEL | the construction was at gable level by 22May 2023 | https:// | image/jpeg
oc4ids-iuq5r5_502 | 207 | projectPlan | construction of junju girls hostel | this is the physical design the contractor was given and he is following it | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_502 | 400 | JUNJU, PHOKA, T/A KACHULU | Point | 34.045258;-10.697503 | RU | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_502 | 146 | Rumphi District Council | 0000 | Rumphi | Northern Region | 0000 | Malawi | Rumphi District Council | 0000 | 0000 | https://0000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_502 | 265 | National Local Goverment | Lilongwe | Lilongwe |  |  | Malawi | National Local Goverment | gsgsf@mnd.com | 000 |  | funder