## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget
oc4ids-iuq5r5_560 | Construction of 10,000 Houses for Security Institution Phase 1 | The 10,000 housing for security institutions project is a national initiative by the Government of Malawi, through the Ministry of Lands, Housing and Urban Development, to provide decent accommodation for the members of the Malawi Police Service, the Malawi Defence Force, the Malawi Prison Service and the Department of Immigration and Citizenship Services. | The 10,000 housing for security institutions project is a national initiative by the Government of Malawi, through the Ministry of Lands, Housing and Urban Development, to provide decent accommodation for the members of the Malawi Police Service, the Malawi Defence Force, the Malawi Prison Service and the Department of Immigration and Citizenship Services. | construction | implementation | 2023-06-20T09:46:56Z | 2021-04-01T00:00:00Z | 2025-03-31T00:00:00Z | 1460 | governance;socialHousing | 0.00

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_560 | 410 | 13/2020 | Construction of 40 Houses at Mvera Support Battalion | Construction of 40 Housing Units | active | construction | 2284132030.32 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2284132030.32 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 411 | 06/2020 | Construction of 25 Houses at Ipyana PMS and Songwe Police | Costruction of 15 Houses at Ipyana and 10 House at Songwe Police | active | construction | 1300795693.17 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1300795693.17 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 412 | 08/2020 | Construction of 30 Houses at Mzuzu Prison and Jenda Police | Construction of 20 Houses at Mzuzu Prison and 10 Houses at Jenda Police | closed | construction | 1689152375.99 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1689152375.99 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 413 | 13/2020 | Construction of 51 Houses at Area 45 Immigration | Construction of 51 Houses at Area 45 Immigration | active | construction | 2431698212 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2431698212 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 414 | 17/2020 | Construction of 50 Houses at Area 30 Police HQ | Construction of 50 Houses at Area 30 Police HQ | active | construction | 2370629193 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2370629193 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 415 | 20/2020 | Construction of 15 Houses at Mangochi Malamya PMS | Construction of 15 Houses at Mangochi Malamya PMS | closed | construction | 1212294289.77 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1212294289.77 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 416 | 28/2020 | Construction of 20 Houses in Neno and Mwanza | Construction of 10 Houses in Neno and 10 Houses in Mwanza | active | construction | 1384362318.31 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1384362318.31 | MWK | 2021-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 365
oc4ids-iuq5r5_560 | 417 | 013/L/PH/INFRA/17 | Construction of 25 Houses at Lilongwe Prison | Construction of 25 Houses at Lilongwe Prison | active | construction | 2235379805.56 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2235379805.56 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 418 | 09/2020-LOT 7 | Construction of 55 Houses at Engineers Battalion - KU | Construction of 55 Houses at Engineers Battalion - Kasungu | active | construction | 3565790312.08 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3565790312.08 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 419 | 27/2020 | Construction of 30 Houses at Mitole Camp - Chikwawa | Construction of 30 Houses at Mitole Camp - Chikwawa | active | construction | 2156827845.56 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2156827845.59 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 420 | 013/L/PH/INFRA/19 | Construction of 50 Houses in Zomba Changalume | Construction of 50 Houses in Zomba Changalume | active | construction | 3422894248.9 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3422894248.9 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 421 | 013/L/PH/INFRA/19 | Construction of 50 Houses at Malawi Police - Mzuzu City | Construction of 50 Houses at Malawi Police - Mzuzu City | active | construction | 3866876304.68 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3866876304.68 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 422 | 013/L/PH/INFRA/24A | Construction of 20 Houses at Malawi Police - Blantyre City | Construction of 20 Houses at Malawi Police - Blantyre City | active | construction | 1954861434.06 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1954861434.06 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 423 | 26/2020B | Construction of 20 Houses in Blantyre City - Malawi Prison | Construction of 20 Houses in Blantyre City - Malawi Prison | active | construction | 1909649340.38 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1909649340.38 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 424 | 16/2020 | Construction of 49 Houses at Malawi Immigration - LL | Construction of 49 Houses at Malawi Immigration - Lilongwe | active | construction | 3940842160.76 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3940842160.76 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 425 | 013/L/PH/INFRA/20 | Construction of 35 Houses at Malawi Police - Zomba City | Construction of 35 Houses at Malawi Police - Zomba City | active | construction | 2945165097.3 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 2945165097.3 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 426 | N/A | Construction of 55 Houses for Malawi Defence Force - Meru Batallion Chitipa | Construction of 55 Houses for Malawi Defence Force at Meru Batallion - Chitipa | active | construction | 4884014861.93 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 4884014861.93 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 427 | 013/L/PH/INFRA/22C | Construction of 15 Houses at Mount Pleasant Police - Blantyre | Construction of 15 Houses at Mount Pleasant Police - Blantyre | active | construction | 1179179262.22 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1179179262.22 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 428 | 02/2020-LOT 3 | Construction of 15 Houses at Chitipa Prison | Construction of 15 Houses at Chitipa Prison | active | construction | 1235299078.8 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1235299078.8 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 429 | 12/2020A | Construction of 19 Houses at Mvera Support Batallion | Construction of 19 Houses at Mvera Support Batallion | active | construction | 1630714443.29 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1630714443.29 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 430 | 25/2020A | Construction of 8 Houses for Malawi Police - Blantyre City | Construction of 8 Houses for Malawi Police - Blantyre City | active | construction | 773319741.41 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 773319741.41 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 431 | 013/L/PH/INFRA/8 | Construction of 55 Houses at Engineers Batallion - KU | Construction of 55 Houses at Engineers Battalion - Kasungu | active | construction | 3720941585.88 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3720941585.88 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 432 | 11/2020-LOT 9 | Construction of 50 Houses at Parachute Battalion - Salima | Construction of 50 Houses at Parachute Battalion - Salima | active | construction | 3472169775.67 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 3472169775.67 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 433 | 013/L/PH/INFRA/16B | Construction of 13 Houses for Malawi Police - Lilongwe City | Construction of 13 Houses for Malawi Police - Lilongwe City | active | construction | 1182344959.16 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1182344959.16 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 434 | 08/2020C | Construction of 12 Houses for Malawi Police - Mzuzu City (moved to KU) | Construction of 12 Houses for Malawi Police - Mzuzu City (moved to Kasungu) | active | construction | 1037662142.23 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1037662142.23 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 435 | 14/2020-LOT 12 | Construction of 15 Houses at Yellow Camp - Mchinji | Construction of 15 Houses at Yellow Camp - Mchinji | active | construction | 1182344959 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1182344959 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 436 | 013/L/PH/INFRA/22B | Construction of 17 Houses at Chilomoni Police | Construction of 17 Houses at Chilomoni Police | active | construction | 1409931270.86 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1409931270.86 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 437 | 013/L/PH/INFRA/23B | Construction of 10 Houses at Kanjedza Police | Construction of 10 Houses at Kanjedza Police | active | construction | 769174699.89 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 769174699.89 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 438 | 013/L/PH/INFRA/16A | Construction of 13 Houses at Lilongwe Police | Construction of 13 Houses at Lilongwe Police | active | construction | 999679196.6 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 999679196.6 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 439 | 03/2020-LOT 1 | Construction of 55 Houses at Meru Battalion - Chitipa | Construction of 55 Houses at Meru Battalion - Chitipa | active | construction | 4542688243.71 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 4542688243.71 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 440 | 12/2020B | Construction of 21 Houses at Fish Eagle - Salima | Construction of 21 Houses at Fish Eagle - Salima | active | construction | 1653080318.14 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1653080318.14 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 441 | 013/L/PH/INFRA/5A | Construction of 12 Houses for Malawi Police - Mzuzu | Construction of 12 Houses for Malawi Police - Mzuzu | active | construction | 1020559704.27 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1020559704.27 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 442 | 18/2020D | Construction of 12 Houses at Police Service - Lilongwe | Construction of 12 Houses at Police Service - Lilongwe | active | construction | 864133772.14 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 864133772.14 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 443 | 013/L/PH/INFRA/16D | Construction of 12 Houses for Lilongwe City Police | Construction of 12 Houses for Lilongwe City Police | active | construction | 857483415.86 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 857483415.86 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 444 | 013/L/PH/INFRA/22A | Construction of 20 Houses at Chichiri Prison - Blantyre | Construction of 20 Houses at Chichiri Prison - Blantyre | active | construction | 1582278675.94 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1582278675.94 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 445 | 013/L/PH/INFRA/5D | Construction of 12 Houses for Malawi Police - Mzuzu | Construction of 12 Houses for Malawi Police - Mzuzu | active | construction | 1129430301.9 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 1129430301.9 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 446 | 08/2020B | Construction of 12 Houses for Malawi Police - Mzuzu | Construction of 12 Houses for Malawi Police - Mzuzu | active | construction | 987300567.11 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 987300567.11 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365
oc4ids-iuq5r5_560 | 447 | 013/L/PH/INFRA/23C | Construction of 10 Houses at Soche Police - Blantyre | Construction of 10 Houses at Soche Police - Blantyre | active | construction | 936293754.65 | MWK | 51 | Malawi Government | 6 | Directorate of Buildings (DoB) | 936293754.65 | MWK | 2021-11-30T00:00:00Z | 2022-11-30T00:00:00Z | 365

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_560 | 438 | Ipyana PMS | KR | Northern | Malawi
oc4ids-iuq5r5_560 | 439 | Songwe Police | KR | Northern | Malawi
oc4ids-iuq5r5_560 | 440 | Mzuzu Prison | MZ | Northern | Malawi
oc4ids-iuq5r5_560 | 441 | Jenda Police | KS | Central | Malawi
oc4ids-iuq5r5_560 | 442 | Mvera Support Battalion | DO | Central | Malawi
oc4ids-iuq5r5_560 | 443 | Area 45 | LL | Central | Malawi
oc4ids-iuq5r5_560 | 444 | Area 30, Police Head Quarters | LL | Central | Malawi
oc4ids-iuq5r5_560 | 445 | Malamya PMS Camp | MG | Southern | Malawi
oc4ids-iuq5r5_560 | 446 | Neno Police | NE | Southern | Malawi
oc4ids-iuq5r5_560 | 447 | Mwanza Police | MW | Southern | Malawi
oc4ids-iuq5r5_560 | 448 | Lilongwe Prison | LL | Central | Malawi
oc4ids-iuq5r5_560 | 449 | Engineers Batallion | KS | Central | Malawi
oc4ids-iuq5r5_560 | 450 | Mitole Camp | CK | Southern | Malawi
oc4ids-iuq5r5_560 | 451 | Changalume | ZO | Southern | Malawi
oc4ids-iuq5r5_560 | 452 | Blantyre City Police | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 453 | Blantyre City Prison | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 454 | Mzuzu City Police | MZ | Northern | Malawi
oc4ids-iuq5r5_560 | 455 | Lilongwe Immigration | LL | Central | Malawi
oc4ids-iuq5r5_560 | 456 | Zomba City Police | ZO | Southern | Malawi
oc4ids-iuq5r5_560 | 457 | Meru Battalion MDF | CT | Northern | Malawi
oc4ids-iuq5r5_560 | 458 | Mount Pleasant Police | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 459 | Chitipa Prison | CT | Northern | Malawi
oc4ids-iuq5r5_560 | 460 | Mvera Support Battalion | DO | Central | Malawi
oc4ids-iuq5r5_560 | 461 | Parachute Battalion | SA | Central | Malawi
oc4ids-iuq5r5_560 | 462 | Lilongwe City Police | LL | Central | Malawi
oc4ids-iuq5r5_560 | 463 | Yellow Camp | MC | Central | Malawi
oc4ids-iuq5r5_560 | 464 | Chilomoni Police | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 465 | Kanjedza Police | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 466 | Lilongwe Police | LL | Central | Malawi
oc4ids-iuq5r5_560 | 467 | Soche Police | BT | Southern | Malawi
oc4ids-iuq5r5_560 | 468 | Fish Eagle | SA | Central | Malawi
oc4ids-iuq5r5_560 | 469 | Mzuzu Police | MZ | Northern | Malawi
oc4ids-iuq5r5_560 | 470 | Lilongwe Police Service | LL | Central | Malawi
oc4ids-iuq5r5_560 | 471 | Chichiri Prison | BT | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/address/region | parties/0/address/postalCode | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url
oc4ids-iuq5r5_560 | 6 | Directorate of Buildings (DoB) | Capital Hill | Lilongwe | Malawi | Directorate of Buildings (DoB) | Email@email.com | 00000000 | administrativeEntity
oc4ids-iuq5r5_560 | 51 | Malawi Government | Capital Hill | Lilongwe | Malawi | Malawi Government | info@malawi.gov.mw | 0000 | funder;procuringEntity | Central Region | 0000 | 0000 | https://www.malawi.gov.mw
oc4ids-iuq5r5_560 | 117 | DEC Construction | 0000 | Blantyre | Malawi | DEC Construction | 0000 | 0000 | contractor | Southern Region | 0000 |  | https://0000
oc4ids-iuq5r5_560 | 189 | Pams Construction | P.O. Box 1286, Blantyre | Blantyre | Malawi | Pams Construction | 0000 | +265999 940 005 | contractor | Southern Region | 0000
oc4ids-iuq5r5_560 | 295 | Tapita/Donekis Construction | Lilongwe | Lilongwe | Malawi | Tapita/Donekis Construction | @gmail.com | 0000 | contractor
oc4ids-iuq5r5_560 | 350 | FUKUMELE BUILDING CONTRACTORS | Lilongwe | Lilongwe | Malawi | FUKUMELE BUILDING CONTRACTORS | @gmail.com | 0000 | contractor