## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate
oc4ids-iuq5r5_70 | Development of a Robust Standardization, Quality Assurance, Accreditation and Metrology (SQAM) Infrastructure in Malawi | Construction of Office and Laboratory Complex | To build capacity in regulating requirements of the Malawi Bureau of Standards (MBS) by improving testing requirements and thereby contribute to the improvement of export trade, economic improvement and welfare of Malawians | construction | implementation | 2022-08-30T10:23:34Z | 2016-02-01T00:00:00Z | 2018-01-31T00:00:00Z | 2022-09-30T00:00:00Z | 2433 | economy | 2022-10-01T00:00:00Z | 2062-09-30T00:00:00Z | 2072-09-30T00:00:00Z | 18262 | 0.00 | 2022-09-30T00:00:00Z

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_70 | 34 | 114 | MOD Chartered Architects
oc4ids-iuq5r5_70 | 40 | 73 | Terrastone Construction Limited

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_70 | 34 | 114 | MOD Chartered Architects
oc4ids-iuq5r5_70 | 40 | 31 | City Building Contractor
oc4ids-iuq5r5_70 | 40 | 43 | SINOHYDRO CORPORATION LTD
oc4ids-iuq5r5_70 | 40 | 73 | Terrastone Construction Limited

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays | contractingProcesses/0/summary/ocid
oc4ids-iuq5r5_70 | 34 | Design and Supervision | Project Design and Supervision | active | supervision | open | bestValueToGovernment | 1 | 413812900 | MWK | 109 | Malawi Bureau of Standards (MBS) | 6 | Directorate of Buildings (DoB) | 413812900 | MWK | 2016-02-01T00:00:00Z | 2018-01-31T00:00:00Z | 2022-09-30T00:00:00Z | 2433
oc4ids-iuq5r5_70 | 40 | Construction | Construction of Laboratory and Office Complex | active | construction | open | bestValueToGovernment | 3 | 18276239600 | MWK | 109 | Malawi Bureau of Standards (MBS) | 6 | Directorate of Buildings (DoB) | 18276239599.7 | MWK | 2016-02-01T00:00:00Z | 2018-01-31T00:00:00Z | 2022-09-30T00:00:00Z | 2433 | SQAM

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/datePublished | documents/0/dateModified | documents/0/format | documents/0/accessDetails | documents/0/author
oc4ids-iuq5r5_70 | 47 | illustration | EXTERIOR VIEW | One of the sides of the building snapped from outside | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 48 | illustration | Laboratory | One of the Testing Laboratories | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg
oc4ids-iuq5r5_70 | 52 | illustration | CORRIDOR | Picture of one of the corridors Administration block | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 53 | illustration | BOARD ROOM | The Boardroom still under final touches, basically now waiting for carpeting | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 54 | illustration | AUDITORIUM | The Auditorium in its final stages, awaiting fixing of seats | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 55 | illustration | EXTERIOR VIEW 2 | Another angle of the building captured from outside | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 56 | illustration | ELEVATOR | Elevator captured being finalised. | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office
oc4ids-iuq5r5_70 | 57 | illustration | CORRIDOR 2 | Another Corridor on the testing block | https:// | 2022-08-24T00:00:00Z | 2022-08-24T00:00:00Z | image/jpeg | Captured the building by camera | Standards Information Office

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_70 | 70 | Plot No. BE 495, Behind Trade Fair Grounds | Point | [35.030899,-15.7984] | Ali Hassan Mwinyi Road | BT | Southern | P O Box 946, BLANTYRE | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/address/region | parties/0/address/postalCode | parties/0/contactPoint/url | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_70 | 6 | Directorate of Buildings (DoB) | Capital Hill | Lilongwe | Malawi | Directorate of Buildings (DoB) | Email@email.com | 00000000 | administrativeEntity
oc4ids-iuq5r5_70 | 31 | City Building Contractor | P.O. Box 30213, Blantyre | Blantyre | Malawi | City Building Contractor | cbc@globemw.net | 0999 964 358 | tenderer | Southern Region | 0000
oc4ids-iuq5r5_70 | 43 | SINOHYDRO CORPORATION LTD | Box 1256, Lilongwe | Lilongwe | Malawi | SINOHYDRO CORPORATION LTD | info@sinohydro.com | 0997 675 053 | tenderer | Central Region | 0000 | https://www.sinohydro.com
oc4ids-iuq5r5_70 | 51 | Malawi Government | Capital Hill | Lilongwe | Malawi | Malawi Government | info@malawi.gov.mw | 0000 | funder | Central Region | 0000 | https://www.malawi.gov.mw | 0000
oc4ids-iuq5r5_70 | 73 | Terrastone Construction Limited | P.O Box 995,Lilongwe | Lilongwe | Malawi | Terrastone Construction Limited | mail@mail.com | 0888 829 227 | supplier;tenderer | Central
oc4ids-iuq5r5_70 | 109 | Malawi Bureau of Standards (MBS) | Malawi Bureau of Standards Moirs Road P.O Box 946 Blantyre Malawi | Blantyre | Malawi | Malawi Bureau of Standards (MBS) | mbs@mbsmw.org | +2651 870 488 | funder;procuringEntity | Southern Region |  | https://mbsmw.org/
oc4ids-iuq5r5_70 | 114 | MOD Chartered Architects | M O D Chartered Architects Address: Cnr Glyn Jones & Sharpe Rd, Blantyre, Malawi City of Malawi | Blantyre | Malawi | MOD Chartered Architects | 0000 | 0000 | supplier;tenderer | Southern Region | 0000 | https://0000