## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/maxExtentDate | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_711 | Construction of (5) market toilets at Mizimu, Mwanakhu, Lauderdale and Chikuse and Chimbalanga | The project involved the Construction of (1 ) double-hole market toilet at Mizimu, Mwanakhu, Chikuse, Lauderdale and Chimbalanga | To enhance sanitation within the markets and also to increase revenue generation for the Council | construction | completion | 2023-09-06T18:15:37Z | 2022-11-07T00:00:00Z | 2023-01-31T00:00:00Z | 85 | waterAndWaste | 2023-09-06T00:00:00Z | 2022-11-25T00:00:00Z | 2022-12-05T00:00:00Z | 23395840 | MWK | 2023-02-13T00:00:00Z | The projects were successfully completed | Twenty three million three hundred ninety five thousand eight hundred and forty kwacha | 1 double holed toilet was constructed at each market | 1 double holed toilet was constructed at each market | 23395840 | MWK