## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/maxExtentDate | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_712 | Rehabilitation of Tcherekere Irrigation Scheme intake weir 1 | The project was involving the Rehabilitation of Tcherekere Irrigation Scheme and the intake weir | To increase crop production and crop diversification among surrounding communities | rehabilitation | completion | 2023-09-06T18:25:48Z | 2022-11-07T00:00:00Z | 2023-01-31T00:00:00Z | 2023-01-31T00:00:00Z | 85 | economy.agriculture | 2023-09-06T00:00:00Z | 2022-11-25T00:00:00Z | 2022-12-05T00:00:00Z | 24738302.93 | MWK | 2023-02-13T00:00:00Z | The project was completed successfully | Twenty four million seven hundred thirty eight thousand three hundred and two kwacha ninety three tambala | The rehabilitation works of the irrigation scheme and the intake weir completed successfully | The rehabilitation works of the irrigation scheme and the intake weir completed successfully | 24738302.93 | MWK