## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/maxExtentDate | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_715 | Rehabilitation of Chitakale Market Sheds | The project was involving the Rehabilitation of Chitakale Market Shed and butchery | To increase sanity in the market and also to enhance revenue generation within the market | rehabilitation | completion | 2023-09-06T18:59:56Z | 2022-11-07T00:00:00Z | 2023-01-31T00:00:00Z | 85 | economy | 2023-09-06T00:00:00Z | 0.00 | 2023-02-13T00:00:00Z | The project was completed successfully | Thirty million seven hundred seventy nine thousand five hundred ninety eight kwacha ninety two tambala | 1 market shed and 1 butchery rehabilitated | 1 market shed and 1 butchery rehabilitated | 30779598.92 | MWK

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_715 | 556 | The Project is located in Kumwamba village, Group Village Headman Tchete along Limbe-Muloza Road in Mulanje District | Along Limbe-Muloza Road at Chitakale Trading Centre | MU | Southern | Private Bag 9, Mulanje | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_715 | 68 | Mulanje District Council | along Kara O Mulla road | Mulanje | Southern | Private Bag 9 | Malawi | Mulanje District Council | mulanjecouncil@gov.mw | 09000000000 | administrativeEntity