## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_744 | Construction of 3 No. Block of 2 bedroom Flats at Nandolo in Zomba | 3 No. 2 bedroom Flats | Providing Safety ,Comfort and affordable to the Nation | construction | cancelled | 2023-09-11T05:51:46Z | 2019-03-28T00:00:00Z | 2020-05-30T00:00:00Z | 429 | socialHousing | 2018-12-20T00:00:00Z | 2020-02-01T00:00:00Z | 739244998.15 | MWK | 2020-05-30T00:00:00Z | The contract was terminated due to Non Performance by the contractor -New Contractors will be identified to complete the works. | 488839492.06 | MWK