## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_80 | MBERA RESOURCE CENTRE | CONSTRUCTION OF MBERA RESOUCE CENTRE CLASS ROOM BLOCK AND 2 VIP PITLATRINE TOILETS | IMPROVING ACCESS TO INFORMATION | construction | decommissioning | 2025-08-15T10:28:47Z | 2021-12-13T00:00:00Z | 2022-03-30T00:00:00Z | 2022-08-30T00:00:00Z | 260 | communications | 2022-09-01T00:00:00Z | 2052-12-27T00:00:00Z | 2062-08-25T00:00:00Z | 14603 | 0.00 | 2022-04-30T00:00:00Z | the project was completed within the implementation period | Completed without additional costs | Completed according to scope | Main building and two toilets were all completed according to scope | 27931635 | MWK

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_80 | 525 | 380 | INTERPAVE 2010 CONSTRUCTION

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_80 | 525 | 380 | INTERPAVE 2010 CONSTRUCTION
oc4ids-iuq5r5_80 | 525 | 385 | Marshall Construction
oc4ids-iuq5r5_80 | 525 | 137 | Mathews Phiri Civil Engineering
oc4ids-iuq5r5_80 | 525 | 252 | Moprom Construction
oc4ids-iuq5r5_80 | 525 | 138 | Mwaka Civil and Building Contractor

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_80 | 525 | BDC/IPDC/RFQ/GESD 2021-2022/06 | Mbera Youth Resource Centre Contract details | Mbera Youth Resource Centre Contract details | closed | construction | open | bestValueToGovernment | 5 | 27931635 | MWK | 69 | Balaka District Council | 69 | Balaka District Council | 27931615 | MWK | 2022-01-05T00:00:00Z | 2022-03-22T00:00:00Z | 2022-09-05T00:00:00Z | 243

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_80 | 479 | socialImpact | Social and Environmental impact Report | Social and Environmental impact Report | https:// | application/pdf
oc4ids-iuq5r5_80 | 480 | environmentalImpact | Site Environmental Management Report | GESD and DDF projects Site Environmental Management Report | https:// | application/pdf
oc4ids-iuq5r5_80 | 481 | feasibilityStudy | Technical appraisal report | Site Technical appraisal report | https:// | application/pdf
oc4ids-iuq5r5_80 | 482 | costBenefitAnalysis | Technical Appraisal | Assessment of potential benefits of the construction project to community | https:// | application/pdf
oc4ids-iuq5r5_80 | 487 | maintenancePlan | Maintence Plan | Maintenance plan for buildings | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_80 | 282 | STA Mbera | Balaka North Constituency, Liwawazi Ward | BA | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_80 | 69 | Balaka District Council | off balaka main road next to Meru filling station | Balaka | South | P/Bag 1 | Malawi | Balaka District Council | gamafrancis6@gmail.com | 265 1 552 049 | 265 1 552 050/790 | http://balakadistrictcouncil.com | procuringEntity;administrativeEntity
oc4ids-iuq5r5_80 | 137 | Mathews Phiri Civil Engineering | P.O. Box 314, Zomba | Zomba | Southern Region | 0000 | Malawi | Mathews Phiri Civil Engineering | 0000 | +265995219619 |  | https://0000 | tenderer
oc4ids-iuq5r5_80 | 138 | Mwaka Civil and Building Contractor | P.O. Box 55. Liwonde | Liwonde | Southern Region | 0000 | Malawi | Mwaka Civil and Building Contractor | 0000 | +265999896395 |  | https://0000 | tenderer
oc4ids-iuq5r5_80 | 252 | Moprom Construction | P.O. Box 30922, Lilongwe | Lilongwe | Central | P.O. Box 30922, Lilongwe | Malawi | Moprom Construction | moprom@gmail.com | 08840921121 | 0000 |  | tenderer
oc4ids-iuq5r5_80 | 380 | INTERPAVE 2010 CONSTRUCTION | Lilongwe | Lilongwe |  |  | Malawi | INTERPAVE 2010 CONSTRUCTION | @gmail.com | 0000 |  |  | tenderer;supplier
oc4ids-iuq5r5_80 | 385 | Marshall Construction | Zomba | Zomba |  |  | Malawi | Marshall Construction | @gmail.com | 0000 |  |  | tenderer

## soc_consultationMeetings
id | social/0/consultationMeetings/0/id | social/0/consultationMeetings/0/date | social/0/consultationMeetings/0/numberOfParticipants | social/0/consultationMeetings/0/address/streetAddress | social/0/consultationMeetings/0/address/locality | social/0/consultationMeetings/0/address/region | social/0/consultationMeetings/0/address/countryName
oc4ids-iuq5r5_80 | 6 | 2022-08-18T00:00:00Z | 8 | Mbera site | TA Kachenga | South | Malawi

## social
id | social/0/landCompensationBudget/amount | social/0/landCompensationBudget/currency
oc4ids-iuq5r5_80 | 0