## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_809 | NASONJO BRIDGE | construction of nasonjo bridge | to facilitate the accessibility of social services | construction | completion | 2025-02-19T07:12:27Z | 2024-05-06T00:00:00Z | 2024-07-06T00:00:00Z | 61 | 2024-02-08T00:00:00Z | 2024-02-08T00:00:00Z | 38241707.5 | MWK | 2024-07-06T00:00:00Z | completed | Nasonjo bridge | the project was completed in time | 38241707.5 | MWK