## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency | social/inIndigenousLand
oc4ids-iuq5r5_81 | CHIMATIRO MATERNITY WING | CONSTRUCTION OF CHIMATIRO MATERNITY WING, SEPTIC TANK, PLACENTA PIT AND WATER TANK | IMPROVING ACCESS TO MATERNAL HEALTH | construction | decommissioning | 2025-08-15T13:37:23Z | 2021-12-13T00:00:00Z | 2022-04-30T00:00:00Z | 2022-09-30T00:00:00Z | 291 | health | 2022-10-03T00:00:00Z | 2052-12-27T00:00:00Z | 2062-08-25T00:00:00Z | 14571 | 2021-11-09T00:00:00Z | 2021-11-29T00:00:00Z | 44155453.17 | MWK | 2023-09-01T00:00:00Z | The project was completed within the implementation period | completed with additional cost | Completed with additional External works | Main clinic block, placenta pit, ash pit, incinerator | 67344480.52 | MWK | FALSE

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/uri | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_81 | 1 | 58 | CHIMATIRO MATERNITY WING | https://WWWW.balakadc.com | 44155453.17 | MWK | 2021-12-13T00:00:00Z | 2022-04-30T00:00:00Z | 2022-09-30T00:00:00Z | 69 | Balaka District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_81 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_81 | 523 | 137 | Mathews Phiri Civil Engineering

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_81 | 523 | 380 | INTERPAVE 2010 CONSTRUCTION
oc4ids-iuq5r5_81 | 523 | 137 | Mathews Phiri Civil Engineering
oc4ids-iuq5r5_81 | 523 | 252 | Moprom Construction

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_81 | 523 | BDC/IPDC/RFQ/GESD 2021-2022/1 | Chimatiro Maternity Contract details | Chimatiro Maternity Contract details | closed | construction | open | bestValueToGovernment | 3 | 75000000 | MWK | 69 | Balaka District Council | 69 | Balaka District Council | 67344480.43 | MWK | 2023-07-03T00:00:00Z | 2024-03-14T00:00:00Z | 2024-07-31T00:00:00Z | 394

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_81 | 471 | environmentalImpact | Environmental Impact Assessment Report | Environmental Impact Assessment Report | https:// | application/pdf
oc4ids-iuq5r5_81 | 472 | socialImpact | Social Impact Assessment Report | Social Impact Assessment Report | https:// | application/pdf
oc4ids-iuq5r5_81 | 473 | feasibilityStudy | Feasibility-Site Appraisal | Site Appraisal for project Implementation | https:// | application/pdf
oc4ids-iuq5r5_81 | 474 | costBenefitAnalysis | Site Appraisal Report | Site appraisal report for project implementation highlight potential benefits of the structure | https:// | application/pdf
oc4ids-iuq5r5_81 | 488 | maintenancePlan | Buildings Maintenance Plan | Buildings Maintenance Plan | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_81 | 87 | TA SAWALI/CHIMATIRO VDC/ NEAR SAWALI TRADING CENTRE/NKHONDE WARD/ BALAK CENTRAL EAST | SAWALI TRADING CENTRE | BA | Southern | 1 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_81 | 69 | Balaka District Council | off balaka main road next to Meru filling station | Balaka | South | P/Bag 1 | Malawi | Balaka District Council | gamafrancis6@gmail.com | 265 1 552 049 | 265 1 552 050/790 | http://balakadistrictcouncil.com | procuringEntity;administrativeEntity
oc4ids-iuq5r5_81 | 137 | Mathews Phiri Civil Engineering | P.O. Box 314, Zomba | Zomba | Southern Region | 0000 | Malawi | Mathews Phiri Civil Engineering | 0000 | +265995219619 |  | https://0000 | supplier;tenderer
oc4ids-iuq5r5_81 | 252 | Moprom Construction | P.O. Box 30922, Lilongwe | Lilongwe | Central | P.O. Box 30922, Lilongwe | Malawi | Moprom Construction | moprom@gmail.com | 08840921121 | 0000 |  | tenderer
oc4ids-iuq5r5_81 | 380 | INTERPAVE 2010 CONSTRUCTION | Lilongwe | Lilongwe |  |  | Malawi | INTERPAVE 2010 CONSTRUCTION | @gmail.com | 0000 |  |  | tenderer

## soc_consultationMeetings
id | social/consultationMeetings/0/id | social/consultationMeetings/0/date | social/consultationMeetings/0/numberOfParticipants | social/consultationMeetings/0/address/streetAddress | social/consultationMeetings/0/address/locality | social/consultationMeetings/0/address/region | social/consultationMeetings/0/address/countryName
oc4ids-iuq5r5_81 | 4 | 2023-07-30T00:00:00Z | 15 | Chimatiro | Sawali | South | Malawi