## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_875 | Construction of OPD, Laboratory and External Works at Mwangala Health Center | Construction of OPD, Laboratory and External Works at Mwangala Health Center | Construction of OPD, Laboratory and External Works at Mwangala Health Center | rehabilitation | completion | 2025-05-22T15:43:04Z | 2023-11-06T00:00:00Z | 2024-06-05T00:00:00Z | 2024-06-30T00:00:00Z | 237 | health | 2023-11-06T00:00:00Z | 2024-06-05T00:00:00Z | 2034-06-05T00:00:00Z | 3864 | 2024-01-01T00:00:00Z | 2024-01-29T00:00:00Z | 573301200.94 | MWK | 2024-06-05T00:00:00Z | The Project HAs been completed | 464469035.42 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_875 | 1 | 368 | Contract Amount | 573307956.41 | MWK | 2023-11-06T00:00:00Z | 2024-06-05T00:00:00Z | 2024-06-29T00:00:00Z | 408 | Prows Civil

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_875 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_875 | 497 | 408 | Prows Civil

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_875 | 497 | 408 | Prows Civil

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_875 | 497 | NLGFC-MOH-WORKS/12/2022 | Construction of OPD Laboratory and External Works at Mwangala Health Center | Construction of OPD, Laboratory and External Works at Mwangala Health Center | active | construction | open | bestValueToGovernment | 1 | 573307956.41 | MWK | 41 | Dowa District Council | 41 | Dowa District Council | 573307956.41 | MWK | 2023-11-06T00:00:00Z | 2024-06-05T00:00:00Z | 2024-06-30T00:00:00Z | 237

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_875 | 418 | completionCertificate | Completion Certificate | Completion Certificate | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_875 | 609 | Mwangala Health Center | Mwangala Trading Center | DO | Central | 204106 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url
oc4ids-iuq5r5_875 | 41 | Dowa District Council | Private Bag 2 | Dowa | Central | Dowa | Malawi | Dowa District Council | bandanoelsk@live.com | 0999632510 | administrativeEntity;procuringEntity
oc4ids-iuq5r5_875 | 51 | Malawi Government | Capital Hill | Lilongwe | Central Region | 0000 | Malawi | Malawi Government | info@malawi.gov.mw | 0000 | funder | 0000 | https://www.malawi.gov.mw
oc4ids-iuq5r5_875 | 408 | Prows Civil | Lilongwe | P.O. Box 1064, Lilongwe | Central | 000 | Malawi | Prows Civil | prowcivils@outlook.com | 0993333883 | contractor;tenderer;supplier