GOVERNMENT OF MALAWI

# CONTRACT NO.: NS/IPADC/GESD/WKS/2021-22/01-LOT 3

For the

Procurement of Works

Between

THE GOVERNMENT OF THE REPUBLIC OF MALAWI

Acting through

# MINISTRY OF LOCAL GOVERNMENT,

NTCHISI DISTRICT COUNCIL

And

Hiltons Construction.

CamScanne

r

CamScanne

r

General Conditions of Contract

Table of Clauses

1.	Definitions	9

2.	Language and Law	10

3.	Project Manager’s Decisions	10

4.	Communications	10

5.	Subcontracting	10

6.	Other Suppliers	10

7.	Personnel	11

8.	Contractor’s Risks	11

9.	Insurance	11

(a)loss of or damage to the Works, Plant, and Materials;	11

(b)loss of or damage to Equipment;	11

(c)loss of or damage to property (except the Works, Plant, Materials, and Equipment) in

connection with the Contract; and	11

(d)personal injury or death and Third Party liability.	11

10.	Contractor to Construct the Works	11

11.	The Works to Be Completed by the Intended Completion Date	11

12.	Safety	11

13.	Disputes	12

14.	Procedure for Disputes	12

15.	Program	12

16.	Extension of the Intended Completion Date	12

17.	Delays Ordered by the Project Manager	12

18.	Early Warning	13

19.	Correction of Defects	13

20.	Uncorrected Defects	13

21.	Bill of Quantities or Activity Schedule	13

(a)An Admeasurement Contract with a Bill of Quantities, subject to Option 1;or	13

(b)A Lump Sum Contract with an Activity Schedule, subject to Option 2,	13

22.	Change in the Bill of Quantities or Activity Schedule	13

23.	Variations	14

24.	Payment for Variations	14

25.	Payment Certificates	14

26.	Payments	14

27.	Compensation Events	15

(a)The Employer does not give access to a part of the Site by the Site Possession Date

stated in the Special Conditions of Contract.	15

(b)The Project Manager orders a delay or does not issue Drawings, Specifications, or

instructions required for execution of the Works on time.	15

(c)	The Project Manager instructs the Contractor to uncover or to carry out additional tests

upon work, which is then found to have no Defects.	15

(d)	Other suppliers, contractors, public authorities, utilities, or the Employer cause delay

or extra cost to the Contractor.	15

(e)The advance payment is delayed.	15

(f)The Project Manager unreasonably delays issuing a Certificate of Completion.	15

28.	Currencies	15

29.	Retention	15

30.	Liquidated Damages	15

31.	Advance Payment	16

32.	Securities	16

33.	Dayworks	16

34.	Cost of Repairs	16

35.	Completion	16

36.	Taking Over	16

37.	Final Account	16

38.	Termination	17

(a)the Contractor stops work for twenty-eight (28) days when no stoppage of work is

shown  on the current Program and the stoppage has not been authorised by the Project

Manager;.17

(b)the Project Manager instructs the Contractor to delay the progress of the Works, and

the instruction is not withdrawn within twenty-eight (28) days;	17

(c)	the Employer or the Contractor is made bankrupt or goes into liquidation other than for

a reconstruction or amalgamation;	17

(d)	a payment certified by the Project Manager is not paid by the Employer to the

Contractor within ninety (90) days of the date of the Project Manager’s certificate;	17

(e)	the Project Manager gives Notice that failure to correct a particular Defect is a

fundamental breach of Contract and the Contractor fails to correct it within a reasonable

period of time determined by the Project Manager;	17

(f)	the Contractor has delayed the completion of the Works by the number of days for

which the maximum amount of liquidated damages can be paid, as defined in the Special

Conditions of Contract; and	17

(g)	if the Contractor, in the judgement of the Employer has engaged in corrupt, fraudulent,

collusive or coercive practices in competing for or in executing the Contract.	17

39.	Payment upon Termination	18

40.	Property	18

41.	Force Majeure	18

42.	Release from Performance	18

General Conditions of Contract

| - Definitions |  |  |  |
| --- | --- | --- | --- |
| - The following words and expressions shall have the meanings hereby assigned to them: - The “Activity Schedule” means the priced Activity Schedule forming part of the Bid for a Lump Sum Contract. - An “Admeasurement Contract” means a contract based on a priced Bill of Quantities or schedule of unit price rates in which payment to the Contractor is subject to measurement of physical quantities of items by the Employer. - The “Adjudicator” is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in Clauses 13 and 14 hereunder. - “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid for an Admeasurement contract. - “Compensation Events” are those defined in Clause 27 hereunder. - The “Completion Date” is the date of completion of the Works as certified by the Project Manager, in accordance with Sub-Clause 35.1. - The “Contract” is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. - The “Contract Price” is the price stated in the Notice of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract. - “Contractor” means the Supplier appointed under the Contract for the performance of the Works. - “Days” are calendar days; “months” are calendar months. - “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant. - A “Defect” is any part of the Works not completed in accordance with the Contract. - The “Defects Liability Certificate” is the certificate issued by Project Manager upon correction of defects by the Contractor. - The “Defects Liability Period” is the period named in the Special Conditions of Contract and calculated from the Completion Date. - “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract. - “Employer” means the Procuring Entity who employs the Contractor to carry out the Works. - “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. - The “Initial Contract Price” is the Contract Price listed in the Employer’s Notice of Acceptance. - The “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Special Conditions of Contract. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. - “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works. - “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. - The “Procuring Entity” is the party who employs the Contractor to carry out the Works. - The “Project Manager” is the person named in the Special Conditions of Contract (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. - The “Site” is the area defined as such in the Special Conditions of Contract. - “Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site. - “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. - The “Start Date” is given in the Special Conditions of Contract. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any Site Possession Dates. - A “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. - The “Supplier” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring Entity. - The “Contractor’s Bid” is the completed bidding document submitted by the Contractor to the Procuring Entity. - “A “Variation” is an instruction given by the Project Manager which varies the Works. - The “Works” are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Special Conditions of Contract. |  |  |  |
| - Language and Law |  |  |  |
| - The language of the Contract is English and the governing law is that of Republic of Malawi. |  |  |  |
| - Project Manager’s Decisions |  |  |  |
| - Except where otherwise specifically stated and subject to any restrictions in the Special Conditions of Contract, the Project Manager will decide contractual matters between the Employer and the Contractor in the role representing the Employer. |  |  |  |
| - Communications |  |  |  |
| - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |  |  |  |
| - Subcontracting |  |  |  |
| - The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations. |  |  |  |
| - Other Suppliers |  |  |  |
| - The Contractor shall cooperate and share the Site with other suppliers, contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Suppliers, as referred to in the Special Conditions of Contract. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Suppliers, and shall notify the Contractor of any such modification. |  |  |  |
| - Personnel |  |  |  |
| - The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Special Conditions of Contract, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. - If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven (7) days and has no further connection with the work in the Contract. |  |  |  |
| - Contractor’s Risks |  |  |  |
| - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are the Contractor’s risks. |  |  |  |
| - Insurance |  |  |  |
| - The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Special Conditions of Contract for the following events which are due to the Contractor’s risks: - loss of or damage to the Works, Plant, and Materials; - loss of or damage to Equipment; - loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and - personal injury or death and Third Party liability. |  |  |  |
| - Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval before the Start Date. All such insurance shall provide for compensation to be payable as required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. |  |  |  |
| - Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. |  |  |  |
| - Contractor to Construct the Works |  |  |  |
| - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |  |  |  |
| - The Works to Be Completed by the Intended Completion Date |  |  |  |
| - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |  |  |  |
| - Safety |  |  |  |
| - The Contractor shall be responsible for the safety of all activities on the Site. |  |  |  |
| - Disputes |  |  |  |
| - If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within fourteen (14) days of the notification of the Project Manager’s decision. |  |  |  |
| - Procedure for Disputes |  |  |  |
| - The Adjudicator shall give a decision in writing within twenty-eight (28) days of receipt of a notification of a dispute. - The Adjudicator shall be paid by the hour at the rate specified in the Special Conditions of Contract, together with reimbursable expenses of the types specified in the Special Conditions of Contract, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within twenty-eight (28) days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above twenty-eight (28) days, the Adjudicator’s decision will be final and binding. - The arbitration shall be conducted in accordance with the arbitration procedure published by the institution named and in the place shown in the Special Conditions of Contract. - Should an Adjudicator resign or die, or should the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within thirty (30) days, the Adjudicator shall be designated by the Appointing Authority designated in the Special Conditions of Contract at the request of either party, within fourteen (14) days of receipt of such request. |  |  |  |
| - Program |  |  |  |
| - Within the time stated in the Special Conditions of Contract, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. |  |  |  |
| - The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the Special Conditions of Contract. - The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |  |  |  |
| - Extension of the Intended Completion Date |  |  |  |
| - The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |  |  |  |
| - Delays Ordered by the Project Manager |  |  |  |
| - The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |  |  |  |
| - Early Warning |  |  |  |
| - The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |  |  |  |
| - Correction of Defects |  |  |  |
| - The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Special Conditions of Contract. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |  |  |  |
| - Uncorrected Defects |  |  |  |
| - If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will be liable for this amount. The amount will be deducted from current and future payment certificates, or paid by the Contractor if insufficient funds are due under the contract. |  |  |  |
| - Bill of Quantities or Activity Schedule |  |  |  |
| - This Contract is: - An Admeasurement Contract with a Bill of Quantities, subject to Option 1; or - A Lump Sum Contract with an Activity Schedule, subject to Option 2, - as indicated in the Special Conditions of Contract. Option 1: Bill of Quantities for Admeasurement Contract - The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |  |  |  |
| Option 2: Activity Schedule for Lump Sum Contract - The Contractor shall provide updated Activity Schedules within fourteen (14) days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be co-ordinated with the activities on the Program. - The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately. |  |  |  |
| - Change in the Bill of Quantities or Activity Schedule |  |  |  |
| Option 1: Changes in the Bill of Quantities for Admeasurement Contracts - If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than twenty-five (25) percent, provided the change exceeds one (1) percent of the Initial Contract Price, the Project Manager shall adjust the rate or price to allow for the change. - The Project Manager shall not adjust rates or prices from changes in quantities if thereby the Initial Contract Price is exceeded by more than five (5) percent, except with the prior approval of the Employer. - If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. Option 2: Changes in the Activity Schedule for Lump Sum Contracts - The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule. |  |  |  |
| - Variations |  |  |  |
| - All Variations shall be included in updated Programs (or in the case of Lump Sum Contracts in updated Programs and Activity Schedules) produced by the Contractor. |  |  |  |
| - Payment for Variations |  |  |  |
| - The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. - For Admeasurement Contracts only, if the work in the Variation corresponds with an item description in the Bill of Quantities, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |  |  |  |
| - If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. |  |  |  |
| - If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. - The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. |  |  |  |
| - Payment Certificates |  |  |  |
| - The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed and materials on site less the cumulative amount certified previously. - The Project Manager shall check the Contractor’s executed work and materials on site and certify the amount to be paid to the Contractor. - The value of work executed and materials on site shall be determined by the Project Manager. |  |  |  |
| - Payments |  |  |  |
| - Payments shall be adjusted for deductions for advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within thirty (30) days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing and add normal absolute net adjustment of price differences. |  |  |  |
| - Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |  |  |  |
| - Compensation Events |  |  |  |
| - The following shall be Compensation Events: - The Employer does not give access to a part of the Site by the Site Possession Date stated in the Special Conditions of Contract. - The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. - The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. - Other suppliers, contractors, public authorities, utilities, or the Employer cause delay or extra cost to the Contractor. - The advance payment is delayed. - The Project Manager unreasonably delays issuing a Certificate of Completion. |  |  |  |
| - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. - The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor not having given early warning. |  |  |  |
| - Currencies |  |  |  |
| - Payments shall only be made in Malawi Kwacha. |  |  |  |
| - Retention |  |  |  |
| - The Employer shall retain from each payment due to the Contractor the proportion stated in the Special Conditions of Contract until Completion of the whole of the Works. - On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. - With the approval of the Employer, the Contractor may substitute retention money with an “on demand” Bank guarantee. |  |  |  |
| - Liquidated Damages |  |  |  |
| - The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Special Conditions of Contract for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Special Conditions of Contract. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. |  |  |  |
| - Advance Payment |  |  |  |
| - The Employer shall make advance payment of the amount stated in the Special Conditions of Contract against provision by the Contractor of an Unconditional Bank Guarantee, in a form and by a bank acceptable, to the Employer. - The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, to be recovered within one half of the completion period. |  |  |  |
| - Securities |  |  |  |
| - The Performance Security shall be provided to the Employer no later than twenty-one (21) days after receipt of the Notice of Acceptance and shall be issued in the form of a Guarantee in the format specified in the contract and in an amount specified in the Special Conditions of Contract and by a bank acceptable to the Employer. The Performance Security shall be valid until a date twenty-eight (28) days from the date of issue of the Certificate of Completion. |  |  |  |
| - Dayworks |  |  |  |
| - If applicable, the Dayworks rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. - All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two (2) days of the work being done. - The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |  |  |  |
| - Cost of Repairs |  |  |  |
| - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |  |  |  |
| - Completion |  |  |  |
| - The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager will do so upon deciding that the work is completed. |  |  |  |
| - Taking Over |  |  |  |
| - The Employer shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a Certificate of Completion. |  |  |  |
| - Final Account |  |  |  |
| - The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within thirty (30) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within thirty (30) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |  |  |  |
| - Termination |  |  |  |
| - The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. - Fundamental breaches of Contract shall include, but are not limited to, the following: |  |  |  |
| - the Contractor stops work for twenty-eight (28) days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager; |  |  |  |
| - the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within twenty-eight (28) days; - the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; - a payment certified by the Project Manager is not paid by the Employer to the Contractor within ninety (90) days of the date of the Project Manager’s certificate; |  |  |  |
| - the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; - the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Special Conditions of Contract; and - if the Contractor, in the judgement of the Employer has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in executing the Contract. |  |  |  |
| - For the purpose of this paragraph: - "corrupt practice" means the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the procurement process or in contract execution. - "fraudulent practice" means a misrepresentation of facts in order to influence a procurement process or the execution of a contract; - “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Employer, designed to establish prices at artificial, noncompetitive levels; and - “coercive practices” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in a procurement process, or affect the execution of a contract. |  |  |  |
| - When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under Sub-Clause 38.2 above, the Project Manager shall decide whether the breach is fundamental or not. - Notwithstanding the above, the Employer may terminate the Contract for convenience. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |  |  |  |
| - Payment upon Termination |  |  |  |
| - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Special Conditions of Contract. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. - If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |  |  |  |
| - Property |  |  |  |
| - All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |  |  |  |
| - Force Majeure |  |  |  |
| - For purposes of this Clause, “Force Majeure” means an event or situation beyond the control of the Contractor that is not foreseeable, is unavoidable, and its origin is not due to negligence or lack of care on the part of the Contractor. Such events may include, but not be limited to, acts of the Employer in its sovereign capacity, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes. - If a Force Majeure situation arises, the Contractor shall promptly notify the Employer in writing of such condition and the cause thereof. Unless otherwise directed by the Employer in writing, the Contractor shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event. - The Contractor shall not be liable for forfeiture of its performance security or retention monies held, liquidated damages, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contract is the result of an event of Force Majeure. |  |  |  |
| - Release from Performance |  |  |  |
| - If the Contract is frustrated by an event of Force Majeure or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |  |  |  |

SECTION 6 - ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY REQUIREMENTS

Bidders should integrate environmental protection, occupational and community health and safety, gender, equality, child protection, vulnerable people (including those with disabilities), sexual harassment, gender-based violence (GBV), sexual exploitation and abuse (SEA), HIV/AIDS awareness and prevention and wide stakeholder engagement in the planning processes, programs, and activities of the parties involved in the execution of the Works. The Roads Authority may prescribe additional issues to be included which may also address: climate adaptation, land acquisition and resettlement, indigenous people, etc. The Environmental, Social Health and Safety activities will be implemented throughout the construction phase and the client will be closely monitoring with the aim of continuously improving processes and activities and for reporting on the compliance with the ESHS Policy

For the purpose of the ESHSS policy and/or code of conduct, the term “child” / “children” means any person(s) under the age of 18 years

As a minimum, the policy is set out to the commitments to:

apply good international industry practice

to protect and conserve the natural environment and to minimize unavoidable impacts;

provide and maintain a healthy and safe work environment and safe systems of work;

protect the health and safety of local communities and users, with particular concern for those who are disabled, elderly, or otherwise vulnerable;

ensure that terms of employment and working conditions of all workers engaged in the Works meet the requirements of the ILO labour conventions to which the host country is a signatory;

be intolerant of, and enforce disciplinary measures for illegal activities. To be intolerant of, and enforce disciplinary measures for GBV, inhumane treatment, sexual activity with children, and sexual harassment;

incorporate a gender perspective and provide an enabling environment where women and men have equal opportunity to participate in, and benefit from, planning and development of the Works;

work co-operatively, including with end users of the Works, relevant authorities, contractors and local communities;

engage with and listen to affected persons and organisations and be responsive to their concerns, with special regard for vulnerable, disabled, and elderly people;

provide an environment that fosters the exchange of information, views, and ideas that is free of any fear of retaliation, and protects whistleblowers;

minimise the risk of HIV transmission and to mitigate the effects of HIV/AIDS associated with the execution of the Works;

The policy should be signed by the senior manager of the Employer. This is to signal the intent that it will be applied rigorously.

Minimum Content of ESHS requirements

In preparing detailed specifications for ESHS requirements, the specialists should refer to and consider:

project reports e.g. ESIA/ESMP

consent/permit conditions

required standards including World Bank Group EHS Guidelines

relevant international conventions or treaties etc., national legal and/or regulatory requirements and standards (where these represent higher standards than the WBG EHS Guidelines)

relevant international standards e.g. WHO Guidelines for Safe Use of Pesticides

relevant sector standards e.g. EU Council Directive 91/271/EEC Concerning Urban Waste Water Treatment

grievance redress mechanism including types of grievances to be recorded and how to protect confidentiality e.g. of those reporting allegations of GBV/SEA

GBV/SEA prevention and management

The detail specification for ESHS should, to the extent possible, describe the intended outcome rather than the method of working.

The ESHS requirements should be prepared in manner that does not conflict with the relevant General Conditions of Contract and Particular Conditions of Contract, and in particular:

General Conditions of Contract

Sub-clause 3 	Language and Law

Sub-clause 7.1	Subcontracting

Sub-clause 8.1	Other Contractors

Sub-clause  9        Personnel and Equipment

Sub-clause 12       Contractor’s Risks

Sub-clause 15.1 	Contractor to Construct the Works

Sub-clause 18	Safety and Protection of the Environment

Sub-clause 19.1 	Discoveries

Sub-clause 31       Early Warnings

Sub-clause 41.4    Payments

Minimum Requirements for the BIDDER’S Code of Conduct

[A minimum requirement for the Code of Conduct should be set out by the Employer, taking into consideration the issues, impacts, and mitigation measures identified, for example,  in :

project reports e.g. ESIA/ESMP

any particular GBV/SEA requirements

consent/permit conditions (regulatory authority conditions attached to any permits or approvals for the project)

required standards including World Bank Group EHS Guidelines

relevant international conventions, standards or treaties, etc., national legal and/or regulatory requirements and standards (where these represent higher standards than the WBG EHS Guidelines)

relevant  standards e.g. Workers’ Accommodation: Process and Standards (IFC and EBRD)

relevant sector standards e.g. workers accommodation

grievance redress mechanisms.

The types of issues identified could include. risks associated with: labor influx, spread of communicable diseases, sexual harassment, gender based violence, illicit behavior and crime, and maintaining a safe environment etc.]

[Amend the following instructions to the Bidder taking into account the above considerations.]

A satisfactory code of conduct will contain obligations on all Contractor’s personnel (including sub-contractors and day workers) that are suitable to address the following issues, as a minimum.  Additional obligations may be added to respond to particular concerns of the region, the location and the project sector or to specific project requirements.  The code of conduct shall contain a statement that the term “child” / “children” means any person(s) under the age of 18 years.

The issues to be addressed include:

Compliance with applicable laws, rules, and regulations

Compliance with applicable health and safety requirements to protect the local community (including vulnerable and disadvantaged groups), the Employer’s and Project Manager’s personnel, and the Contractor’s personnel, including sub-contractors and day workers, (including wearing prescribed personal protective equipment, preventing avoidable accidents and a duty to report conditions or practices that pose a safety hazard or threaten the environment)

The use of illegal substances

Non-Discrimination in dealing with the local community (including vulnerable and disadvantaged groups), the Employer’s and Project Manager’s personnel, and the Contractor’s personnel, including sub-contractors and day workers (for example on the basis of family status, ethnicity, race, gender, religion, language, marital status, age, disability (physical and mental), sexual orientation, gender identity, political conviction or social, civic, or health status)

Interactions with the local community(ies), members of the local community (ies), and any affected person(s) (for example to convey an attitude of respect, including to their culture and traditions)

Sexual harassment (for example to prohibit use of language or behavior, in particular towards women and/or children, that is inappropriate, harassing, abusive, sexually provocative, demeaning or culturally inappropriate)

Violence including sexual and/or gender based violence (for example acts that inflict physical, mental or sexual harm or suffering, threats of such acts, coercion, and deprivation of liberty

Exploitation including sexual exploitation and abuse (for example the prohibition of the exchange of money, employment, goods, or services for sex, including sexual favors or other forms of humiliating, degrading behavior, exploitative behavior or abuse of power)

Protection of children (including prohibitions against sexual activity or abuse, or otherwise unacceptable behavior towards children, limiting interactions with children, and ensuring their safety in project areas)

Sanitation requirements (for example, to ensure workers use specified sanitary facilities provided by their employer and not open areas)

Avoidance of conflicts of interest (such that benefits, contracts, or employment, or any sort of preferential treatment or favors, are not provided to any person with whom there is a financial, family, or personal connection)

Respecting reasonable work instructions (including regarding environmental and social norms)

Protection and proper use of property (for example, to prohibit theft, carelessness or waste)

Duty to report violations of this Code

Non retaliation against workers who report violations of the Code, if that report is made in good faith.

The Code of Conduct should be written in plain language and signed by each worker to indicate that they have:

received a copy of the code;

had the code explained to them;

acknowledged that adherence to this Code of Conduct is a condition of employment; and

understood that violations of the Code can result in serious consequences, up to and including dismissal, or referral to legal authorities.

A copy of the code shall be displayed in a location easily accessible to the community and project affected people. It shall be provided in languages comprehensible to the local community, Contractor’s personnel (including sub-contractors and day workers), Employer’s and Project Manager’s personnel, and affected persons.

Payment for ESHS Requirements

The Employer’s ESHS and procurement specialists should consider how the Contractor will cost the delivery of the ESHS requirements. In the majority of cases, the payment for the delivery of ESHS requirements shall be a subsidiary obligation of the Contractor covered under the prices quoted for other Bill of Quantity items or activities. For example, normally the cost of implementing work place safe systems of work, including the measures necessary for ensuring traffic safety, shall be covered by the Bidder’s rates for the relevant works. Alternatively, provisional sums could be set aside for discrete activities for example for HIV counselling service, and, GBV/SEA awareness and sensitization or to encourage the contractor to deliver additional ESHS outcomes

beyond the requirement of the Contract.

SECTION 6- SUPPLEMENTARY INFORMATION

A.    Environmental and Social Impact Management

A 1. 	ENVIRONMENTAL MANAGEMENT TEAM (EMT)

The Contracting Authority will be represented on site by a Regional Roads Engineer (RRE) and his inspection team will include an Environmental Control Officer (ECO) who shall determine members of the site supervision team as the Environmental Management Team (EMT) that will report on the activities to the Contracting Authority through RRE.

The EMT will be responsible for monitoring the performance of the Contractor during the construction phase with regard to Environmental issues and to assess the effectiveness of the impact mitigation measures in protecting the environment on behalf of the District Council and the local communities. The role of the EMT will be “pro-active” with regard to impacts seeking to predict and prevent negative impact and pollution.

The Contractor will provide one full time Contractor’s Health Safety and Environmental Liaison Officer (HSE Officer) to be responsible for the implementation of all environmental mitigation measures. The HSE Officer will also undertake liaison with local community leaders and ensure that the Contractor’s compliance with the requirements of the Malawi Environmental Affairs Department, the District Value’s Office, and other relevant authorities in connection with environmental and social considerations.

The Contractor shall prepare a Project Environmental Management Plan (PEMP) outlined in Clause 8300 and based on the headings, risks and responsibilities given in the EMP Table.

This Plan shall be particular to the works required under this Contract. The draft PEMP will be discussed, reviewed, where necessary amended and finally agreed in the EMT. The PEMP will form the principal document upon which all Environmental Monitoring will be based throughout the project.

A 2.  IMPACT MITIGATION MEASURES

A 2.1.  	LANDSCAPE PRESERVATION

General

The Contractor shall exercise care to conserve the natural landscape and shall conduct his construction operations so as to prevent any unnecessary destruction, scarring, or defacing of the natural surroundings in the vicinity of the works.  Except where clearing is required for permanent works, diversions or excavation operations, all trees, native shrubbery and vegetation shall be preserved and shall be protected from damage by the contractor’s construction operation and equipment.  The edges of clearing and cuts through trees, shrubbery, and vegetation shall be irregularly shaped to soften the undesirable visual impact of straight lines.  Movement of labour and equipment within the right-of-way and over routes provided for access to the work shall be performed in a manner to prevent damage to grazing land, crops or property.

Except as otherwise provided special reseeding or replanting will not be required under these specifications; however on completion of the work all work areas not seeded shall be scarified and left in a condition which will facilitate natural re-vegetation provided for proper drainage and prevent erosion.  All unnecessary destruction, scarring, damage or defacing reseeded or the landscape resulting from the Contractor’s operations shall be repaired, replanted reseeded or otherwise corrected as directed by the Regional Roads Engineer and at the Contractor’s expense.

Construction Roads

The location, alignment, and grade of construction roads shall be subject to approval of the Resident Engineer. When no longer required by the Contractor, construction roads shall, if required by the Resident Engineer, be restored to the original contour and made impassable to vehicular traffic.  The surfaces of such diversions shall be scarified as needed to provide a condition that will facilitate natural re-vegetation provided for proper drainage and prevent erosion.

Construction Facilities

The Contractor’s workshops office and yard area shall be located and arranged in a manner to preserve trees and vegetation to the maximum practicable extent. On completion of the project all temporary buildings including concrete footings and slabs, and all construction materials and debris shall be removed from the site.  The area shall be

regarded, as required, so that all surfaces drain naturally, blend with natural terrain, and are left in a condition that will facilitate natural re-vegetation, provide for proper drainage and prevent erosion.

Blasting Precautions

In addition to any requirements of local regulations, the contractor shall adopt precautions when using explosives that will prevent scattering rocks, stumps, or other debris outside the work area, and prevent damage to surrounding trees, shrubbery and vegetation.

A 2.2.	PRESERVATION OF TREES AND SHRUBBERY

Preservation

All trees and shrubbery which are not specifically required to be cleared or removed for construction purposes shall be protected from any damage that may be caused by the construction operations and equipment. Special care shall be exercised where trees or shrubs are exposed to injuries by construction equipment, blasting excavating, dumping, chemical damage or other operations; and the Contractor shall adequately protect such trees by use of protective barriers or other methods approved by the Regional Roads Engineer.  The removal of trees or shrubs will only be permitted after prior approval by the Regional Roads Engineer.

The layout of the Contractor’s construction facilities such as workshops, warehouse storage areas and parking areas; location of access and haul routes; and operation in borrow and spoil areas shall be planned and conducted in such a manner that all trees and shrubbery not approved for removal by the Resident Engineer shall be preserved and adequately protected from either direct or indirect damage by the Contractor’s operations.

Except in emergency cases or when otherwise approved by Regional Roads Engineer, trees shall not be used as anchorages. Where such use is approved, the trunk shall be wrapped in with a sufficient thickness of approved protective material before any rope, cable, or wire is placed.

Repair or Treatment of Damage

The Contractor shall be responsible for injuries to trees and shrubs caused by his operations.  The term “injury” shall include without limitation, bruising, scarring, tearing and breaking of roots, trunk or branches. All injured trees and shrubs shall be repaired or treated without delay, at the Contractor’s expense.  If damage occurs, the Regional Roads Engineer will determine method of repair or treatment to be used for injured trees and shrubs as recommended by an experienced horticulturist or a licensed tree surgeon provided by and at the expense of the Contractor.

Replacement

Trees or Shrubs that in the opinion of the Regional Roads Engineer are beyond savings shall be removed and replaced early in the next planning season.  The replacement shall be the same species or other approved species and of the maximum size that is practicable to plant and sustain growth in the particular environment.  Replacement trees and shrubs shall be stayed, watered and maintained for a period of 1 year from the date of replacement.

A 2.3.	PREVENTION OF WATER POLLUTION

General

The Contractor’s construction activities shall be performed by methods that will prevent entrance or accidental spillage, of solid matter, contaminants, debris, and other pollutants and wastes into streams, flowing or dry watercourses, lakes, and underground water sources, concrete, sanitary waste, industrial waste, radioactive substances, oil and other petroleum products, aggregate processing tailings, mineral salts and thermal pollution.

Dewatering work for structure foundations or earthworks operations adjacent to or encroaching on streams or watercourses shall be conducted in a manner to prevent muddy water and eroded materials from entering the streams or watercourses by construction of intercepting ditches, bypass channels, barriers, settling ponds or by other approved means. Excavated materials or other construction materials shall not be stockpiled or deposited near or on stream banks, lake shorelines or other watercourse perimeters where they can be washed away by high water or storm runoff or can in any way encroach upon watercourse itself.

Turbidity increases in a stream or other bodies of after that are caused by construction activities shall be strictly controlled. When necessary to perform required construction work in a stream channel, the turbidity may be increased, as approved by the Regional Roads Engineer, for the shortest practicable period required to complete such work. This required construction work may include such work as diversion of a stream, construction or removal of cofferdams, specified earthworks in or adjacent to a stream channel, pile driving, and construction of turbidity control structures.  Mechanised equipment shall not be operating in flowing water except as necessary to construct crossing or to perform the required construction.

Wastewater from aggregate processing, concrete batching, or other construction operations shall not enter streams, watercourses, or other surface waters without the use of such turbidity control methods as settling ponds, gravel-filter entrapment dikes, approved flocculating processes that are not harmful to fish, re-circulation systems for washing of aggregates or other approved methods. Any such wastewaters, discharged into surface of these specifications, settleable material is defined as that material possible. For the purpose of these specifications settleable material is defined as material which will settle from the water by gravity during a 1- hour quiescent detention period.

Compliance with law and regulations

The Contractor shall comply with applicable laws and regulations and water quality standards concerning the control and abatement of water pollution.

A 2.4.     ABATEMENT OF AIR POLLUTION

The Contractor shall comply with applicable laws and regulations concerning the prevention and control of air pollution.  Notwithstanding the above in conduct of construction activities and operation of equipment, the Contractor shall utilize such practicable methods and devices as are reasonably available to control prevent and otherwise minimize atmospheric emissions or discharges of air contaminants.

The emission of dust into the atmosphere shall be strictly controlled during the manufacture, handling and storage of concrete and road aggregates, and the Contractor shall use such methods and equipment as are necessary for the collection and disposal or prevention of dust during these operations.  The Contractor’s methods of storing and handling cement and lime shall also include means of eliminating atmospheric discharges of dust.  Equipment and vehicles that show excessive emissions of exhaust gases due to poor engine adjustments or other inefficient operating conditions.  Shall not be operated until corrective repairs or adjustments are made.

Burning of materials resulting from clearing of trees and bush, combustible construction materials, and rubbish will be permitted only when atmospheric conditions for burning are considered favourable and when authorized by the Regional Roads Engineer. In lieu of burning, such combustible materials may be disposed of by other methods as provided in Clause B 2.10 hereof. Where open burning is permitted, the burn piles shall be properly constructed to minimize smoke, and in no case shall unapproved materials such as tires, plastic rubber products, asphalt products, or other materials, that create heavy black smoke or nuisance odours, be burned.

A 2.5.	DUST ABATEMENT

During the performance of the work required by this specifications or any other appurtenant thereto, whether on right-of-way provided by the Employer or elsewhere, the Contractor shall furnish all the labour, equipment, materials, and means required, and shall carry out proper and efficient measures wherever and as often as necessary to reduce the dust nuisance and to prevent dust which has originated from his operations from damaging crops, orchards, cultivated fields and dwellings or causing nuisance to  obtain adequate control.

A 2.6.	NOISE ABATEMENT

The Contractor shall comply with applicable National laws, orders and regulations concerning the prevention, control and abatement of excessive noise.

Blasting, the use of jackhammers, pile driving, rock crushing or other operations producing high-intensity impact noise may be not be performed during the night.

A 2.7.	LIGHT ABATEMENT

The Contractor shall exercise special care to direct all stationary flood-light to shine downwards at an angle less than horizontal.  These floodlights shall also be shielded so as not to be a nuisance to surrounding areas. No lighting shall include a residence in its direct beam.

The Contractor shall be responsible for correcting light problems when they occur as directed by the Resident Engineer.

A 2.8.	PRESERVATION OF HISTORICAL & ARCHAELOGICAL DATA

Should the Contractor or any of his employees in the performance of his contract discover evidence of possible scientific, prehistoric, or archaeological data he will notify the Regional Roads Engineer immediately, giving the location and nature of the findings. Written confirmation shall be forwarded within 2 days.  The Contractor shall exercise care so as not to damage artefacts or fossils uncovered during excavation operation and shall provide such co-operation and assistance as may be necessary to preserve the findings for removal or other disposition by the employer. The Contractor will also report his findings for the Ministry of Forestry, Fisheries and Environmental Affairs and the authority responsible for antiquities.

Where appropriate by reasons of a discovery the Regional Roads Engineer may order delays in the time of performance, or changes in the work, or both. If such delays, or changes or both are ordered, the time of performance and contract price shall be adjusted in accordance with the applicable clause in the conditions of contract.

The Contractor shall insert this Clause in all subcontracts that involve the performance of work on the project site.

A  2.9.	PESTCIDES

Pesticides include herbicides, insecticides, fungicides rodenticides, and pesticides, surface disinfectants animal repellant and insect repellant. Should the Contractor find it necessary to use pesticides in work areas of this contract, he shall submit his plan for such use to the Regional Roads Engineer for written approval.

The Contractor shall read and comply with all labeling requirements when using pesticides.

A2.10.	CLEAN-UP AND DISPOSAL OF WASTE MATERIALS

Clean – Up

The Contractor shall, at all times keep the construction area, including storage areas used free from accumulation of waste material or rubbish.

All waste water and sewerage from office, residential and mobile camps shall be piped to soak pits or other disposal areas constructed in accordance with local government regulations, and where and when regulations require it the Contractor shall obtain a permit or other appropriate documentation approving the disposal methods used.

All used fuels, oils, other plant or vehicle fluids, and old tyres and tubes shall be collected to a central disposal area on a daily basis and disposed of in a manner approved by the Regional Roads Engineer.

Servicing of plant equipment and vehicles shall whenever possible be carried out at a workshop area.  This workshop area shall be equipped with secure storage areas for fuels oils and other fluids and constructed in such a way as to contain any spillage, which may occur, and similar storage where fluids can be stored securely prior to their disposal.

When servicing of plant, equipment and vehicles is carried out away from the workshop area it shall be done at locations and in such a manner as to avoid spillage and contamination of streams and other drainage courses. Any spillage shall be cleaned up by either burning in place or collecting the contaminated soils and burning them at the central disposal area, all to the satisfaction of the Regional Roads Engineer.

Prior to the completion of the work, the Contractor shall remove from the vicinity of the work all facilities, buildings, rubbish, unused materials, concrete forms and other like material, belonging to him or used under his directions during construction.

All work areas shall be graded and left in a neat manner conforming to the natural appearance of the landscape as provided in Clause 8201.

Any residue deposited on the ground from washing out truck mixers, agitating trucks or any other similar concrete operations shall be buried or cleaned up in a manner acceptable to the Regional Roads Engineer.

In the event of the Contractor’s failure to perform the above work, the work may be performed by the Employer at the expense of the Contractor, and his surety or sureties shall be liable therefore.

Disposal of Waste Material

General

Waste materials including, but not restricted to refuse, garbage, sanitary wastes industrial wastes and oil and other petroleum products, shall be disposed of by the Contractor. Disposal of combustible materials shall be by burying, where burial of such materials is approved by the Regional Roads Engineer by burning, where burning of approved materials is permitted; or by removal from the construction area.  Disposal of non-combustible materials shall be by burying where burial of such materials is approved by the Regional Roads Engineer or by removal from the construction area. Waste materials removed from the construction area shall be dumped at an approved dump

Disposal of Material by Burying

Only materials approved by the Regional Roads Engineer may be buried. Burial shall be in pits and the location, size and dept of which shall be approved by the Resident Engineer.  The pits shall be covered by at least 0.6 metre of earth material prior to abandonment.

Disposal of Material by Burning

All materials to be burned shall be piled in designated burning areas in such a manner as will cause the least fire hazards.  Burning shall be through and complete and all charred pieces remaining after burning, except for scattered small pieces, shall be removed from the construction area and disposed of as otherwise provided in this Clause.

The Contractor shall at all times, take special precautions to prevent fire from spreading beyond the piles being burned and shall be liable for any damage caused by this burning operations.  The Contractor shall have available, at all times, suitable equipment and supplies for use in preventing and suppressing fires and shall be subject to all laws and regulations locally applicable for pre-suppression, suppression and prevention of fires.

Disposal of Material by Removal

Material to be disposed of by removal from the construction area shall be removed from the area prior to the completion of the work under these specifications.  All materials removed shall become the property of the Contractor.

Materials to be disposed of by dumping shall be hauled to an approved dump.  It shall be the responsibility of the Contractor to make any arrangements of such dumping.  Any fees for charges required to be paid for dumping of materials shall be paid by the Contractor and shall be included in the prices tendered in the Bill of Quantities for other work.

A 3.	PROJECT ENVIRONMENTAL MANAGEMENT PLAN (PEMP)

The Contractor will be deemed to have prepared his tender upon sound environmental practice and the guidelines contained in this section together with the entire contents of the Guidelines to Environmental Impact Assessment issued by the Ministry of Forestry, Fisheries and Environmental Affairs in December 1997 and the heading applicable to this contract in the Environmental Management Plan that follows this Section; as well as Environmental and Social Management Guidelines in the Road Sector issued by the Roads Authority in March 2008.

The PEMP will be read in conjunction with and shall be deemed to include all descriptions of environmental protection and mitigation described elsewhere in the Specification, Design Standards and Conditions of Contract.  The PEMP will supplement but not supersede normal Regulatory Controls from Health and Safety Inspectorates and shall be made available to all parties.

The following is a summary of the guidelines to be incorporated into the PEMP

Specific proposals

Drainage and Proper installation of drainage structures

Soil erosion

Controlling and management of excavation activities

Installation of erosion control measures such as check dams, scour checks and impact dissipators

Landscaping and re-vegetating road embankment and gravel sites

Pollution (air, noise, water)

Supervision of construction traffic, including control of speed

Sensitisation of workforce

Maintenance of plant and equipment

Proper disposal of construction debris, proper handling, storage and disposal of oil and oil wastes, and disposal of wastewater / sewage at Contractor’s /workmen’s camps

Materials sources

Planned, controlled and restricted access to all materials sites

Proper management of excavation activities

Landscaping terracing where necessary, and grassing and re-vegetation of materials sites

Compensation of individuals/ communities as required for use of material

Controlled blasting of hard stone material

Water Sources

Consultation with communities during identification of sources

Management of water usage

Deviations

Planning of deviations

Reinstating deviations (and old tracks) to original condition

Vegetation

Prohibition of use of herbicides

Landscaping and planting all disturbed areas (pits, deviations, embankments, camps sites)

Planting of trees at main towns/trading centres along road for aesthetics and as pollution screens.

Demobilisation/ Decommissioning

Proper removal and disposal of construction buildings and structures required for the contractors’/workmen’s camp, and construction wastes including oil, solid wastes, and debris after construction works are complete, and restoration to original condition where applicable.

Land/property and crops

Notification to people about non – compensation for annual crops within road reserve

Evaluate land/property loss due to deviations, materials sites and Contractor’s camp

Compensation to be paid for land, crops and all property on land temporarily acquired for road construction works (camps and deviations) and for all crops outside road reserve that are removed/destroyed for clearing of carriageway, gravel pits and deviations

Public Health and Occupational Safety

Provision of water supply for the workforce, and proper facilities for the disposal of solid and sanitary waste

Provision of protective gear to workforce

Provision of a first aid kit on site

Road Safety

Supervision of construction traffic and management of construction activities

Provision of safe access/egress to work sites

Warning signs are erected.

Site of cultural, historical and traditional value

All findings to be reported to the Resident Engineer, RA Ministry responsible for antiquities and Department of Environmental Affairs.

All graves are avoided.

Planning and prevention

Frequency of Environmental site meetings to be chaired by the Environmental Control Officer and attended by relevant parties

Adoption of time scale and planning for all relevant measures

Procedure for correction of bad practice

Reinstatement of borrow pits

Borrow areas

Borrow areas shall be reinstated in compliance with the following minimum specifications in the table below:

PIT AND QUARRY REINSTATEMENT SPECIFICATION

1. At the completion of operations the Contractor shall rehabilitate used, exhausted and obsolete pits and quarries.

2. The sides and floors of pits shall be formed to a flowing finish with side slopes not steeper than 1 vertical to 6 horizontal.

3. During pit reshaping any material carried to the pit shall be spread uniformly over the entire shaped surface. The Contractor shall ensure that non – biodegrable and inert waste is removed and disposed of in licenced sites. The same will apply to toxic waste.

4. Topsoil shall be spread over the shaped batters, filled areas and bare areas of the pits to a reasonable depth.

5. Following the spreading of topsoil, the entire pit shall be ripped along the contours to a depth of 500mm and at not more than 500mm spacing.

REVEGETATION SPECIFICATION

1. Planting and direct seeding shall be carried out after the topsoil has been placed, shaped and prepared for planting and seeding operations

2. The Contractor shall prepare a plant and seed species list that is representative of the native vegetation (trees, and understorey species) in adjacent areas and the list is to be included in the Environmental Management Plan.

3. The plant and seed list shall describe the plant size and spacing of all plants, the quantities by seed species in a seed mix and the seeding rate (kg per hectare) to be used in any revegetation of the area to be rehabilitated.

4. The Contractor shall supply and hand-plant tube stock in good condition using the species and spacing chosen in the plant list.

5. The Contractor shall supply and direct seed the areas to be seeded using the seed species mix and seeding rate (kg per hectare) as described in the plant list.

6. All planting, seeding and or weed control operations shall be undertaken in accordance with basic principles of REVEGETATION AND LANDSCAPING.

7. The completion criteria for revegetation shall be in accordance with the Environmental Management Plan.

A 4.		ENVIRONMENTAL TRAINING

The ECO will be responsible for organising the environmental training of all the Engineer’s and Contractor’s staff.  It is suggested that this training is coupled with the safety training that the Contractor should include in his own site management plan.  The Contractor shall ensure that the Resident Engineer is informed of all staff that will work on the site and their general responsibilities and shall make sure that they are available to attend suitable briefing sessions arranged by the ECO on the environmental mitigation measures that are to be in place on the site.

The Contractor shall provide the ECO with a suitable room for the briefing and such administrative support and facilities as shall be ordered by the ECO.

A 5.	MEDICAL AND HIV/AIDS PREVENTATION PROGRAMMES

To assist in the general health and well being of both all the site staff and the residents in the community local to the works, the Roads Authority will organize and coordinate appropriate awareness training as well as health screening (other than accident prevention and medical aid facilities provided by the Contractor).

The Contractor shall ensure that the Resident Engineer is informed when any new staff commence work on the site such that health and HIV awareness and counseling can be provided either in group sessions or on an individual basis. The Contractor shall ensure that staff are available for briefing by the District Council staff and shall make available suitable rooms, administrative support and provide any facilities or supplies against an order from the District Council. The Contractor shall ensure that condoms provided as part of the HIV/STD control program are readily available to all staff.

The RA will also arrange for the health screening of site workers in local medical facilities and the Contractor shall cooperate fully in these program by making staff available.  The Contractor shall ensure that the Resident Engineer and local medical officials are informed promptly of any workers suffering from the symptoms of infectious disease so appropriate help and treatment can be arranged promptly.

A 6     ROAD SAFETY TRAINING

The District Council will be arranging road safety training and awareness sessions in local schools and community centres.  The Contractor will assist the District Council when requested with administrative support and where ordered the provision of supplies for these courses and program.

A 7   Responsible Authorities

The Contractor is advised that the following authorities have an interest in the environmental and social protective measures associated with this road construction project.

District Assembly Environmental Affairs Department Public Health Department Health and Safety Office District Valuer

A 8	Site Clearance

No trees are to be cut or removed unless required to be cleared or removed for construction works. Where there are branches overhanging roads or traffic diversion routes the Contractor shall agree with the SR the cutting back necessary to provide for clear vehicle access.  The Branch cutting shall then be carried carefully using saws to leave a clean cut face with no damages or snags.

A 9	Finishing of verges and other works area

Verges, routes of diversion roads, site camps and all other areas where the Contractor’s work has heavily compacted the soil shall be loosened, spread with a thin layer of grass plant rich soil and firmed by foot or a light roller so as to encourage the re-growth of natural vegetation.

A 10	Water Pollution

The Contractor shall observe the requirements of Clause 8203 to avoid the pollution of watercourses and ground water. Sanitary facilities for all site workers convenient to the working sites shall be provided to enable environmentally sensitive disposal of the waste.  The storage of bitumen fuel and oil for the works operations shall be arranged in working sites, refueling of all plant and equipment and servicing practices shall be arranged to prevent the uncontrolled spilling of any oil based products.

Mitigation measures shall include drip trays, working on paved surfaces with waste collection arrangements and the provision of oil absorbing material for spills that can be subsequently disposed safely by burning.

Environmental Management Plan Table

| Environmental Social Impact | Proposed Mitigation and Aspect for Monitoring | Responsibility for intervention and monitoring during design, construction and defects liability period |  |  |  |  | Responsibility for mitigation monitoring and/or maintenance after defects liability period | Monitoring means (c) = Construction (o) = operation |  | Recommended frequency of monitoring |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ENVIRONMENTAL MANAGEMENT |  |  |  |  |  |  |  |  |  |  |
| Changes in hydrology impeded drainage | Install drainage structure properly Efficiency of drainage structures |  |  | Design consultant Supervising Engineer Supervising Engineer |  | Contractor District Works Offices |  | Inspection (o) routine maintenance and road condition survey |  | (c ) during construction and on completion of each structure |
| Soil erosion | Control earthworks Install drainage structures properly Install erosion control measures Landscape and re-vegetate gravel sites Management of excavation activities Impact on erosion (on road, off road, embankments, riverbanks etc) Efficiency of erosion control measures Landscape and grass road embankment |  |  | Supervising Engineer and Contractor /DISTRICT COUNCIL District Works Offices DISTRICT COUNCIL |  | Supervising Engineer and Contractor |  | (c ) inspection routine maintenance and road condition survey (c ) inspection routine maintenance and road condition survey |  | (c ) daily erosion control measures during construction and on completion of measures (o ) once in 6 months (c ) once a month |
| Air pollution | Control speed of construction vehicles Prohibit idling of vehicles Sensitive workforce Maintenance of plant and equipment Plant trees in towns as pollution screens Impose speed limits for all vehicles, especially at towns and villages sensitize motorists/road users |  |  | Supervising Engineer and Contractor DISTRICT COUNCIL |  | TA \Health and Environment committees. Traffic police |  | (c ) inspection/ observation (o) observation |  | (c) Daily /random (o) random |
| Air pollution | Control speed of construction vehicles Prohibit idling of vehicles Sensitive workforce Maintenance of plant and equipment Plant trees in towns as pollution screens Impose speed limits for all vehicles, especially at towns and villages sensitize motorists/road users |  |  | Supervising Engineer and Contractor DISTRICT COUNCIL |  | TA \Health and Environment committees. Traffic police |  | (c ) inspection/ observation (o) observation |  | (c) Daily /random (o) random |
| Noise pollution | Sensitize workforce Supervise construction traffic Sensitise drivers of construction vehicles Maintain plant and equipment Impose speed limits for all vehicles, especially at towns and villages Sensitize motorists/road users |  |  | Supervising Engineer and Contractor |  | TA Health and environment Committees Traffic police |  | (c ) inspection/ observation (o) observation |  | Daily /random (o) random |
| Water pollution | Incorporate erosion control measures Works on culverts to be done in the dry season Proper disposal of construction debris Proper handling, storage and disposal of oil and oil wastes Proper disposal of wastewater /sewerage at Contractor’s workmen’s camps |  |  | DISTRICT COUNCIL Supervising Engineer and Constructor |  | Contractor |  | (c ) inspection |  | (c ) daily |
| Oil pollution | Construct parking bays at larger trading centers for heavy vehicles. Proper storage, handling and disposal of oil and oil wastes Maintain plant and equipment Maintenance of construction vehicles should be carried out in the Contractor’s camp |  |  | Design Consultant Supervising Engineer and Contractor Supervising Engineer and Contractor |  | Contractor |  | (c ) Inspection (o) routine maintenance |  | (c ) during construction and on completion (o) once in 6 months (c) daily |
| Gravel sites | Inform people living at/near the sites that the pits have been selected for exploitation. Plan access to gravel sites Control and restrict access to gravel sites (e.g. by fencing ) Control earthworks Proper management of excavation activities Landscape terrace if necessary, and grass site s. Replace trees that were removed during excavation Discourage pits being made into water pans after construction Rehabilitate old unused gravel pits Compensate individuals/ communities as required for use of material Progress of rehabilitated gravel sites (use of site, established vegetation) |  |  | Supervising engineer and Contractor Supervising Engineer and Contractor Contractor Supervising Engineer |  | District Works offices RA |  | ( c) meeting (c ) Inspection (c ) Payment records (o ) Inspection |  | (c ) Once immediately after selection of sites (c ) daily (o) once before excavation begins and at specified periods as agreed thereafter (c ) once in 2 months (o) once in 6 months |
| Hard stone sources | Inform communities living at/near the sites that the sites have been selected for exploitation. Plan access to hard stone sites Control and restrict access to hard stone sites (e.g. by fencing) Control blasting Proper management of exploitation activities Landscape site after exploitation and grass sites. Replace trees or vegetation that were removed during excavation Compensate individuals / communities as required for use of material |  |  | Supervising Engineer and Contractor Supervising Engineer and Contractor Contractor |  |  |  | (c ) meeting (c ) inspection (c ) payments records |  | (c ) Once immediately after selection of sites (c ) daily (o) once before excavation begins and at specified periods as agreed thereafter |
| Sand sources | Take sand from beds of large rivers only Extraction to be done during low flow |  |  | Supervising Engineer and Contractor |  | n/a |  | (c ) inspection |  | (c ) during mining |
| Water sources | Consult with communities during identification of sources Management of water usage |  |  | DISTRICT COUNCIL |  | n/a |  | (c ) meetings, inspection , check plans and schedule |  | ( c) during rains during abstraction at source and at random |
| Deviations | Plans deviations Adhere to road reserve if possible Obtain permission from inhabitant/community if deviation goes beyond road reserve Re instate deviations (and old tracks) to original condition Pay compensation for crops/property removed /destroyed by deviations Monitor rehabilitation of deviations |  |  | Supervising Engineer and Contractor Contractor |  | Contractor District Works Offices RA |  | (c ) check plans inspections (o) Payment records |  | (o) daily when deviations are in use (c ) once before constructing deviations Once in 6 months |
| Vegetation / flora / forests | Control clearing Prohibit clearing using herbicides Replant areas where vegetation is unnecessarily removed Landscaping and planting all disturbed areas (pits, deviations embankments, camp sites) Plant trees at main towns/trading centre s along road |  |  | Supervising Engineer and Contractor TA Health and Environment Committees |  | Contractor |  | ( c) inspection |  | (c ) daily |
|  | Planting and grassing should be done just before the rains Discourage use of firewood/charcoal by providing alternatives Care for tree/plants |  |  |  |  | TA Health and Environment Committees |  | (c ) observation (o ) observation |  | (c ) weekly ( o) Random |
| Workmanship | locate camp in terminal town provide water supply provide proper sanitation facilities on site Provide proper solid waste disposal facilities Have central canteen facilities Discourage use of firewood/charcoal by providing alternatives Manage water use in camps |  |  | Supervising Engineer and Contractor |  | Contractor |  | (c ) inspection |  | (c ) daily |
| Visual Enlargement | Landscaping and planting of deviations, gravel sites and camp Plant trees at terminal towns and trading centers Care for plants and trees |  |  | DISTRICT COUNCIL TA health and Environment committees |  | Contractor TA Health and Environment Committees |  | (c ) inspection (c ) observation (o) observation |  | (c ) daily / random (c ) Weekly (o) random |
| Construction waste | Proper disposal of construction wastes including oil, solid wastes and debris |  |  | Supervising Engineer and Contractor |  | Contractor |  | (c ) inspection |  | (c ) weekly |
| Demobilisation | Clean up site Remove all debris Remove to original condition |  |  | Supervising Engineer and Contractor |  | Contractor |  | (c ) inspection and certificate of completion |  | (c ) on completion of road construction works |
| SOCIAL MITIGATION |  |  |  |  |  |  |  |  |  |  |
| Settlement | Plan for increased population and subsequent expansion of terminal towns and trading centers Conduct STD/AIDS awareness campaign Plan for local security |  | District Physical Planning Department Supervising Engineer TAs |  | District Physical Planning Department |  |  | (c ) meetings, barazas (o) reports (c ) inspection records (c ) meetings, deployment of local police | (c ) once during construction (o) annually (c ) continuous (c ) continuous (o ) continuous |  |
| Loss of Land /property | Identify project affected people Notify people about non-compensation for annual crops within road reserve Evaluate land/property loss due to deviations, materials sites and contractor’s camp Compensation to be paid for land and all property on land to temporally acquired for road construction works |  | DISTRICT COUNCIL Contractor |  | n/a |  |  | (c ) inspection ( c) notices, meetings (c ) inspection (c ) payments records | (c ) Once before construction commences (c ) compensation paid once after assessment of loss before construction |  |
| Loss of crops | Limits clearing of crops as much as possible Pay compensation for all crops outside road reserve that are removed/destroyed for clearing of carriage way , gravel pits and deviations Compensation to be paid for perennial crops within road reserve |  | DISTRICT COUNCIL Supervising Engineer and Contractor DISTRICT COUNCIL |  | Supervising Engineer and Contractor |  |  | (c ) inspector (c ) payment records | (c ) Daily (c ) Once after assessment of loss before construction |  |
| Employment | Recruit local people, of which at least 25% should be women |  | Contractor |  | n/a |  |  | (o) certificate of employment | (o ) quarterly |  |
| Public Health and Occupational safety | Reduce/minimize pollution as above Provide water supply at camps P roper disposal of solid and sanitary waste at camps Design and locate pit latrines prudently Have communal ablution facilities Conduct STD/AIDS awareness campaign and distribute condoms Provide potable water for workforce Provision of protective gear to workforce First Aid Kit on site Appoint Health Safety and Environment officer on site Contractor should have workmen’s compensation cover Monitor impact on public health (incidence of malaria, respiratory diseases, STDs HIV/AIDS) |  | Supervising Engineer and Contractor DISTRICT COUNCIL/Ministry of health |  | Contractor DISTRICT COUNCIL/ Ministry of Health |  |  | (c ) Inspection (o) Independent study | (c ) daily (o ) once in 6 months |  |
| Disturbance to public | Minimise pollution as above Erect information and warning signs Control construction activities Construct special parking bay at terminal towns for trucks/heavy vehicles |  | Supervising Engineer Supervising Engineer Supervising Engineer and Contractor Design Consultant |  | Contractor District Works Offices |  |  | ( c) Inspection ( c) Inspection ( c) Inspection ( c) Inspection (o) routines maintenance | (c ) daily (c ) when affected (c ) daily (c ) during construction and on completion (o ) once in 6 months |  |
| Road Safety | Install speed bumps near school and trading centres Supervise construction traffic Ensure safe access/egress to work sites Erect warning signs Construct shoulders which can be used by pedestrians and non-motorized traffic Construct special parking bay at large trading centres for trucks/heavy vehicles Impact on road safety (number of accidents) |  | Design Engineer Supervising Engineer and Contractor Design Consultant |  | Supervising Engineer and Contractor District Works Offices District Works offices DISTRICT COUNCIL |  |  | (o) (c) Inspection (c) Inspection (o) routines maintenance (c) Inspection (o) routine maintenance (o) Police report | c ) daily ( c) when designed (o) once in 6 months |  |
| Sites of cultural historical and traditional value | Report all findings to Supervising Engineer, RA, Ministry responsible for antiquities and DEA Avoid all graves |  | Supervising Engineer and Contractor |  | n/a |  |  | (c ) Inspection and report | (c ) As need arises |  |
| Socio-economic status | Changes in income level Change in health status Changes in education levels |  | n/a |  | DISTRICT COUNCIL |  |  | (o) Independent Study | (o) once in 5 years |  |
| Land use | Change in land use area covered by settlement, arable land, pasture, degraded land shrub/bushland, social land |  | n/a |  | District Agriculture Offices District Physical Planning Dept |  |  | (o) Independent Study | (o) once in 5 years |  |
| Economic activity in project area | Changes in agricultural production and marketing Changes in livestock production and marketing |  | n/a |  | District Agricultural Officers/DISTRICT COUNCIL |  |  | (o) Independent study | (o) once in 5 years |  |

B.   ADDITIONAL INFORMATION

B 1. STAFF CONDITIONS

The wages paid to staff employed by the contractor shall be fair and reasonable having regard to those commonly paid in the trade or industry in which such staff are employed and undertake to comply with such requirements relating to hours of work and conditions of labour as are or are or may from time to time be laid down in the legislation of Malawi.

In the event of any difference or dispute arising as to what wages ought to be paid, or what hours of working conditions ought to be observed it shall be reported to the Secretary of labour  as prescribed under the Trade Disputes (Arbitration and Settlement) Act (Cap. 54.02 for settlement.

Without prejudice to his obligations under Section 43 of the Employment Act (Cap 55:02)., the Contractor shall keep proper wages books and time sheets showing the wages paid and the time worked by the staff under his employment in and about the carrying out of this Contract and such wages books and time sheets shall be produced whenever required for inspection on of any officer authorized by the Contracting authority.

The Contractor shall recognize the freedom of his employees to be members of Trade Unions.

The Contractor shall at all times during the continuance of the Contract display a copy of this Article  in full on his Site Office  notice boards for the information of his employees.

Due precautions shall be taken by the contractor, and at his own cost, to ensure the safety of his staff and labour and in collaboration with and to the requirements of the local health authorities, to ensure that medical staff, first aid equipment and stores, sick bay and suitable  ambulance service are available  at camps, housing and  on the site at all times throughout the period of the Contract and that suitable arrangements are made for the prevention of epidemics and for all necessary welfare and hygiene requirements.  The Contractor shall ensure that all his staff is given awareness programmes on HIV/AIDS.

The Contractor shall maintain records of health and safety and make reports concerning the health and safety of his employees as the Resident Engineer may from time to time prescribe.  The Contractor shall at all times take the necessary precautions to protect all staff and labour employed on the site from insect nuisance occasioned by the same.  The contractor shall so far  as is reasonably practicable, having regard to  local conditions, provide on the site an adequate supply of drinking and other water for the use of his  staff and labour.

The Contractor shall report to the Resident Engineer details of any accident as soon as possible after its occurrence.  In the case of a fatality or serious accident, the Contractor shall, in addition, notify the Resident Engineer immediately by the quickest means available.

The Contractor shall make all necessary arrangements for the transport to any place as required for burial of any of his expatriate employee or member of their families who may die in Malawi.  The Contractor shall also be responsible for the transport to the place of origin and burial of any of his local employees who may die while engaged upon the Works.

The Contractor shall at all times take all reasonable precautions for the protection of persons and property in the neighbourhood of the Works

B 2. WORKING OUTSIDE NORMAL WORKING HOURS

If any steps taken by the Contractor for working outside normal working hours are deemed by the Resident Engineer to involve the Contracting Authority in additional supervision costs, such costs shall be notified in advance by the Resident Engineer and shall be recoverable from the Contractor either by direct payment by the Contractor, or to become due to the Contractor and the Resident Engineer shall notify the Contractor accordingly, with a copy to the contracting authority.

If any steps taken by the Contractor involve the Engineer’s junior staff working outside normal working hours, the Contractor shall pay overtime to the Engineer’s junior staff. The procedure for overtime shall be as follows:

Contractor presents to Engineer a request to work overtime

Engineer makes arrangements with his personnel and may or may not accept the request for overtime

When overtime has been worked the concerned Engineer’s personnel shall fill and sign time sheet

The filled time sheet shall then be presented to the contractor for countersigning and certification of the hours worked.

At the end of the month the Engineer aggregates all overtime hours worked in the month and lodges with the contractor a claim for payment of overtime.

When the contractor makes payment the Engineer disburses the money to concerned personnel accordingly.

Special Conditions of Contract

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC).  Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| GCC Clause Reference | Special Conditions |
| --- | --- |
| GCC 1.1 | The name and procurement reference number of the Contract is: NS/IPDAC/GESD/WKS/2021-22/01-Lot 7. The Project Manager is: Director of Works. The Works consist of : Construction of Chandawe health Post. The Site is located at: Chandawe health centre, Chilooko. and is defined in Drawings Nos.: N/A The Start Date shall be: 31st December, 2021. The Intended Completion Date for the Works shall be: 30th March, 2022. The Defects Liability Period shall be: 360 Days from the date of issuance of completion of certificate. |
| GCC 3.1 | The Employer’s specific approval is required for: individual Variations (GCC Clauses 23 and 24) or Compensation Events (GCC Clause 27) or Measurements (GCC Clause 22) which would result in an increase to the Initial Contract Price of more than 5 (five) percent; any new Variations or Compensation Events or Measurements which together with previously approved Variations and Compensation Events and Measurements, would result in an increase to the Initial Contract Price of more than 15 (fifteen) percent. |
| GCC 6.1 | The Schedule of Other Suppliers N/A part of the Contract |
| GCC 7.1 | The Schedule of Key Personnel is part of the Contract |
| GCC 9.1 | The minimum insurance cover and deductibles shall be: - The minimum cover for insurance of the Works, Plant and Materials is: None (b) The maximum deductible for insurance of the Works, Plant and Materials is: None (c) The minimum cover for insurance of Equipment is: None (d) The maximum deductible for insurance of Equipment is: None (e) The minimum cover for insurance of property is: None (f) The maximum deductible for insurance of property is: None (g) The minimum cover for personal injury or death insurance is: None with no deductible. |
| GCC 14.2 | The hourly rate to be paid to the Adjudicator is: N/A Fees and types of reimbursable expenses to be paid to the Adjudicator are: N/A |
| GCC 14.3 | The institution whose arbitration procedures shall be used is: Arbitration in accordance with the Laws of Malawi Arbitration shall take place at: NCIC |
| GCC 14.4 | The Appointing Authority for a replacement Adjudicator is: NCIC |
| GCC 15.1 | The Contractor shall submit a revised Program for the Works within Five (5) days of delivery of the Notice of Acceptance. |
| GCC 15.2 | The period between Program updates is N/A days. |
| GCC 19.1 | The Defects Liability Period is: 360 Days |
| GCC 21.1 | This Contract is a Lump Sum Contract. |
| GCC 26.1 | The rate of interest for late payments is N/A percent. |
| GCC 27.1 | The Site Possession Date shall be: 5 Days |
| GCC 29.1 | The proportion of payments retained is 5% percent. |
| GCC 30.1 | The rate per day for liquidated damages is 0.05% per week percent of the final Contract Price per day. The maximum amount of liquidated damages for the whole of the Works is percent of the final Contract Price. Applicable rate shall not exceed one-half (0.05%) per cent per week for uncompleted works, and the maximum shall not exceed ten (10%) percent of the contract price. |
| GCC 31.1 | The Advance Payment will be equivalent to N/A of the Contract Price. It will be paid to the Contractor no later than 30 days after submission of Advance N/A. |
| GCC 31.3 | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting months after the Start Date and ending months after the Start Date. |
| GCC 32.1 | The Performance Security shall be for Ten (10%) percent of the Contract Price: |
| GCC 39.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is: Ten Percent (10%). |