**

**M’MBELWA DISTRICT COUNCIL**

**Site meeting report**

|  |  |
| --- | --- |
| **Name of Activity:** | Site meeting report- Mbalachanda Police Unit Block and Double Pit Latrine Construction |
| **Date of Activity**: | 17th January 2022 | **Type of Activity:** | Field visit |
| **Location:** | Mbalachanda Ward, T/A Chindi |  |  |
| **Compiled by:** | * E. Adini
 |  |  |
| **Participants**  | **Name**1. W. Msukwa
2. M. Thera
3. E. Adini
 | **Designation**Housing OfficerPublic Works InternMET |  |
| **Programme** |
| **Purpose of site visit:**1. To appraise progress of works at Mbalachanda Police Unit.
 |
| **Project status**:* Mbalachanda Police Unit Block and Double Pit Latrine Construction is a project initially conceived under GESD and works commenced on 06 January 2022.
* Works on the project are being undertaken by Pyramid Building and Civil Engineering and are currently estimated at 20 % completion.
* Slab construction on the site has begun.
* The quality of works is good.

  |
| **Observations**1. The length of the police unit block is 18.4m, width is 8.6m and the width reaching the veranda is 11.8m as outlined on the plan.
2. The project uses cement blocks which are 400\*200\*200 mm in measurement for construction as per guidelines and mixture is of good standard. The contractor uses Akshar cement (32.5N)
3. The concrete slab is being made with a combination of 1 bag of cement to 3 wheelbarrows of sand to 6 wheelbarrows quarry stone.
4. There are a lot of artisans on the construction area which makes the work to be more efficient.
 |
|  **Action Items:** |
| **Action** | **Responsible** | **Due** |
| 1. Contractor has to speed up construction in order to catch up with the set project duration | Contractor | ASAP |